## External Instructions
PPP Procurement Plan
Document Number: PPPG-PR-PLN-00013
Issued for Approval:April 2023
Key for the contract value bands:
| A | <£100k
| B | >£100k < £250k
| C | >£250k < £500k
| D | >£500k < £1m
| E | >£1m < £5m
| F | >£5m < £10m
| G | >£10m < £25m
| H | >£25m
Welcome to the latest quarterly edition of the PPP Procurement Plan.
The purpose of the Procurement Plan is to give you, our current and future supply chain, an insight into what PPP is looking to procure and when, so that you can identify potential opportunities for your organisation.
The Procurement Plan includes: the procuring project; what it is looking to procure; its value; and potential dates for issue of invitation to tender and award.
It also includes a category column, and it is sortable so that you can search and sort by your specific category or categories of interest, or by value, or by date, helping you to quickly identify potential opportunities.
The latest Awarded contracts are also included so that you can track a particular procurement through to award, which further allows you to contact the winning supplier if you feel you may be able to assist them as a sub-supplier.
The Procurement Plan is openly available to all and is equally applicable if you are a large company or an SME. It allows you to see our forward programme of potential work, to use as an opportunities register, and also as a networking tool to build your network of suppliers to the nuclear industry and potential future ventures.
Please note Key Delivery Partner (KDP) call offs are not included in this plan however the KDPs will release their own procurement plans.
If you are interested in any of the packages noted within the Procurement Plan please contact pppsupplychain@sl-ppp.co.uk
As part of its pioneering approach to project delivery and local impact, PPP has engaged with the Swimming with the Big Fish SME Matchmaker Service, which brokers introductions and develops relationships between those bidding to become Key Delivery Partners and high performing SMEs willing to invest in West Cumbria. These SMEs plan to create additional jobs, recruit apprentices and invest to expand/ create new facilities in the West Cumbria as a result of the work they do with their respective Key Delivery Partners.
To find out more about the SME Matchmaker Service, contact Luke.dicicco@solomonseurope.co.uk
We are always looking at ways to improve our communications with our supply chain therefore we would welcome any feedback you have to clare.wilson@sl-ppp.com
Programme and Project Partners (PPP) is a 20-year framework let by Sellafield Ltd in 2019 to improve delivery of its major programmes and projects. PPP is formed by four Lot Partners plus Sellafield Ltd as the fifth Partner. The four Lot Partners are:
KBR – Integration Partner
Jacobs – Design Partner
Morgan Sindall Infrastructure – Construction Partner
Doosan Babcock – Process Construction Partner
The programme of work will be worth approximately £7bn across its 20-year life.

## Procurement Plan
Project | Procuring Partner | Project Scope / Trade Packs Description | Category 1 | Basis of competition | Contract Type | Value Band | Advert Date | ITT Release Date | Planned Contract Award Date | Actual Contract Award Date | Successful Contractor
Multiple | Jacobs | Design Support to Lot 2 | Design Services / Support | Project - Single Source | NEC PSC | E | N/A | N/A | 2022-05-13 | 2022-05-16 | On Line Design & Engineering Limited (OLG)
Multiple | Jacobs | Design Support to Lot 2 | Design Services / Support | Project - Single Source | NEC PSC | E | N/A | N/A | 2023-03-31 | 2022-06-22 | 360 Energy
SCP | Altrad Babcock | Civils Finishing | Construction | Project - Competitive Tender | NEC-C | G | Complete | Complete | 2023-08-24 | 2022-05-10 | Altrad Support Services Ltd
SCP | Altrad Babcock | Steam & Air Ejectors | Engineering/Manufacturing | Project - Single Source | NEC - SUPPLY | E | Complete | Complete | 2024-06-24 | 2022-05-13 | Edwards High Vacuum International Ltd
Multiple | KBR | Provision of Bus Services for PPP | Transportation | SL - Sole Source | Framework | E | 2021-11-30 | 2022-02-28 | 2024-06-24 | 2022-05-11 | Stagecoach (North West) Limited
PPP Services | KBR | IT - hosting service | Business Support | SL - Single Source | Bespoke | B | Complete | Complete | 2024-06-26 | 2022-04-01 | Microfocus Limited
PPP Services | KBR | Software licences | Business Support | SL - Single Source | Bespoke | B | Complete | Complete | 2024-07-15 | 2022-04-01 | TD Synnex UK Limited (formally Tech Data Limited)
PPP Services | KBR | Credit Scores | Business Support | Project - Single Source | Bespoke | A | N/A | N/A | 2024-11-11 | 2022-05-16 | Creditsafe
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Single Source | NEC PSC | F | N/A | N/A | 2025-09-22 | 2022-04-01 | Assystem Energy & Infrastructure Ltd
SCP | Altrad Babcock | Construction Hoists | Construction | Project - Competitive Tender | Bespoke | E | Complete | Complete | 2025-09-22 | 2022-06-01 | Pegahoist
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Single Source | NEC PSC | F | N/A | N/A | 2025-09-22 | 2022-04-01 | RPS Consulting Services Limited
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Single Source | NEC PSC | F | N/A | N/A | 2025-09-22 | 2022-04-01 | Mott Macdonald Limited
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Single Source | NEC PSC | D | N/A | N/A | 2025-12-08 | 2022-04-01 | PWHytek Limited
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Single Source | NEC PSC | E | N/A | N/A | 2026-01-15 | 2022-04-01 | Orano Limited
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Single Source | NEC PSC | E | N/A | N/A | 2026-08-19 | 2022-04-01 | Wood Group Limited
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Single Source | NEC PSC | D | N/A | N/A | 2027-04-30 | 2022-04-01 | Morson Projects Ltd
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Single Source | NEC PSC | E | N/A | N/A | 2027-05-04 | 2022-04-01 | Frazer-Nash Consultancy Limited
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Single Source | NEC PSC | D | N/A | N/A | 2027-05-26 | 2022-04-01 | Tenet Consultants Ltd
SRP | Morgan Sindall | Window Shielding - Premac including machining | Precision Engineering | Project - Competitive Tender | NEC | E | 2021-06-15 | 2022-02-04 | 2027-10-15 | 2022-07-21 | Permali Deho Limited
PPP Services | KBR | Consultancy Services - Procurement | Business Support | SL - Single Source | NEC PSC | D | Complete | Complete | 2028-02-07 | 2022-04-07 | MACE Limited
SRP | Morgan Sindall | Steam Supply – Thorp – on site works Thorp, SPRS, SRP | Mechanical & Pipework | Project - Competitive Tender | NEC | E | 2021-09-29 | 2022-02-11 | 2028-11-28 | 2022-07-05 | Shepley Engineering Limited
SRP | Morgan Sindall | EC&I fire systems | Electrical & Instrumentation | Project - Single Source | NEC | F | Complete | 2021-11-19 | 2029-05-21 | 2022-04-26 | Protec
SCP | Altrad Babcock | SIXEP Tie in's (PSC) | Engineering/Manufacturing | MPP - Fabrication & Manufacture | NEC - SUPPLY | C | Complete | 2022-02-04 | 2029-09-10 | 2022-06-18 | Ansaldo Nuclear Limited
BEPPS2 | Morgan Sindall | Borehole Sampling and Trailpits - AWARDED | Design Services / Support | Project - Single Source | NEC | B | N/A | 2022-03-18 | 0 | 2022-05-13 | Socotec UK Limited
SRP | Morgan Sindall | Access Equipment - Alimak Hoists | Plant & Equipment and Materials | Project - Competitive Tender | NEC | F | 2021-06-11 | 2021-12-17 | 0 | 2022-07-26 | Alimak Group UK LTD
PPP Services | KBR | Graphic Design | Business Support | Project - Sole Source | Framework | A | Complete | Complete | 0 | 2022-05-25 | Creative in Cumbria
PPP Services | KBR | WIFI Installation | Business Support | Project - Sole Source | Bespoke | A | Complete | Complete | 0 | 2022-06-01 | Avoria IT Services
SCP | Altrad Babcock | Material Handling Equipment (PSC) | Engineering/Manufacturing | Project - Single Source | NEC - SUPPLY | A | Complete | 2022-02-08 | 2023-04-28 | 2022-06-08 | Hosokawa Micron
SRP | Morgan Sindall | Discontinued Cans for FAT / IFAT | Precision Engineering | Project - Competitive Tender | NEC | D | 2021-07-19 | 2022-02-10 | 2023-05-31 | 2022-06-08 | Hyde Group Nuclear Ltd
RAP | Morgan Sindall | MSM's - Testing | Plant & Equipment and Materials | Project - Single Source | Purchase Order | A | N/A | N/A | 2023-05-31 | 2022-06-17 | Walischmiller Engineering GmbH
RAP | Morgan Sindall | MSM's - Testing | Plant & Equipment and Materials | Project - Single Source | Purchase Order | A | N/A | N/A | 2023-05-31 | 2022-06-17 | PAR Systems
SRP | Morgan Sindall | Shield Doors | Precision Engineering | Project - Competitive Tender | NEC | E | Complete | 2022-01-31 | 2023-05-31 | 2022-07-15 | Asturfeito SA
Multiple | KBR | Provision of PPP PPE and PPE Recycling Framework | Consumables | SL - Single Source | Framework | E | 2022-01-29 | 2022-04-29 | 2023-05-31 | 2022-06-30 | Bunzl UK Ltd
SRP | Morgan Sindall | Lifts Process Building – Kone – single source | Construction | Project - Competitive Tender | NEC | D | N/A | 2022-03-14 | 2023-05-31 | 2022-08-01 | Kone Lifts
SRP | Morgan Sindall | Waste management | Waste Management, Disposal & Storage | Project - Competitive Tender | NEC | D | 2022-02-01 | 2022-05-01 | 2023-05-31 | 2022-07-18 | Lawsons
SRP | Morgan Sindall | Mechanical Fabrication (incl's 000/100/200 IWT & SAT support) | Engineering | MPP - Fabrication & Manufacture | NEC - SUPPLY | E | Complete | 2022-02-11 | 2023-05-31 | 2022-07-18 | North West Energy Coast (NWEC Alliance TIS Cumbria & McMenon Engineering Services)
Multiple | Jacobs | Contaminated Land Support | Consultancy | Project - Single Source | Bespoke | D | N/A | N/A | 2023-05-31 | 2022-08-01 | Wood Group Limited
SCP | Altrad Babcock | Process Cabinets(incl Pressure Transducer Cabinets) | Engineering/Manufacturing | MPP - Fabrication & Manufacture | NEC - SUPPLY | E | Complete | 2022-02-09 | 2023-05-31 | 2022-08-18 | North West Energy Coast (NWEC Alliance TIS Cumbria & McMenon Engineering Services)
RAP | Morgan Sindall | Place Level 1A Strip Out Contract | Electrical & Instrumentation | Project - Single Source | NEC | E | 2021-12-22 | 2022-03-22 | 2023-05-31 | 2022-09-06 | Jacobs Field Services
SRP | Jacobs | Design support for Services supports | Design Services / Support | Project - Single Source | NEC PSC | A | N/A | N/A | 2023-05-31 | 2022-09-01 | Hilti GB Limited
SCP | Altrad Babcock | Control Systems (inc SIXEP Control System) | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | F | Complete | Complete | 2023-05-31 | 2022-09-12 | Bilfinger UK
RAP | Morgan Sindall | Bundle 4 (WO2) | Engineering | Framework | NEC | E | N/A | TBC | 2023-05-31 | 2022-10-13 | NIS Limited
RAP | Morgan Sindall | Provision of Construction Management Services | Consultancy | Project - Single Source | NEC PSC | B | N/A | N/A | 2023-05-31 | 2022-10-14 | Regency Consultancy North Yorkshire Limited
RAP | Morgan Sindall | HAASC, MA Cells and SNM Glovebox / VXA ECI | Construction | MPP - Fabrication & Manufacture | NEC | B | Complete | Complete | 2023-05-31 | 2023-02-03 | NIS Limited
SRP | Morgan Sindall | Cranes & Hoists – COTS equipment – Supply & Install | Engineering | Project - Competitive Tender | NEC | D | 2020-08-05 | 2022-03-28 | 2023-05-31 | 2022-12-22 | SCX Projects Ltd
SRP | Morgan Sindall | ECI interim award for tank farm | Engineering | Project - Competitive Tender | Bespoke | A | complete | complete | 2023-05-31 | 2022-12-15 | BOC
SCP | Altrad Babcock | Material Handling Equipment (SC) | Engineering/Manufacturing | Project - Single Source | NEC - SUPPLY | E | Complete | 2022-09-01 | 2023-05-31 | 2023-01-10 | Hosokawa Micron
SCP | Altrad Babcock | Interconnecting Pipework and pipe bridge sumps (East &West Pipe bridge) | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | G | Complete | 2022-04-01 | 2023-05-31 | 2023-01-23 | Shepley Engineering Limited
ILW EZ | Morgan Sindall | Preparatory Civils Works - accommodation/compound/laydown | Construction | Project - Competitive Tender | NEC-A | B | 2021-12-07 | 2022-03-07 | 2023-05-31 | TBC | Not Awarded
RAP | Morgan Sindall | Internal Transfer System - ECI | Plant & Equipment and Materials | Project - Competitive Tender | NEC | C | 2022-08-11 | 2022-11-09 | 2023-07-10 | TBC | Not Awarded
RAP | Jacobs | TW Design validation | Design Services / Support | Project - Single Source | Bespoke | A | N/A | N/A | 2023-07-10 | 2023-03-01 | Morgan Sindall Engineering Solutions Limited
ILW EZ | Morgan Sindall | Earthworks and Civil Construction Works inc P9 Raw/Potable Water | Construction | Project - Competitive Tender | NEC-C | G | 2022-05-21 | 2022-08-19 | 2023-08-31 | TBC | Not Awarded
RAP | Morgan Sindall | Process CCTV - Design | Electrical & Instrumentation | Project - Competitive Tender | NEC | A | N/A | TBC | 2023-08-31 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Surveys (Pre September 2022, Topo etc) | Design Services / Support | Project - Competitive Tender | NEC-A | B | 2022-10-22 | 2023-01-20 | 2023-08-31 | 2023-03-30 | CatSurveys Limited
CDE | KBR | Systems Integration Services Frameworks | IT Hardware and Software | Project - Single Source | Bespoke | E | N/A | N/A | 2023-08-31 | TBC | Not Awarded
CDE | KBR | Systems Integration Services Frameworks | IT Hardware and Software | Project - Single Source | Bespoke | E | N/A | N/A | 2023-08-31 | TBC | Not Awarded
CDE | KBR | PDF viewing, signatures and commenting | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | N/A | N/A | 2023-09-30 | TBC | Not Awarded
CDE | KBR | Requirements Management - production | IT Hardware and Software | Direct Award | Bespoke | B | N/A | N/A | 2023-09-30 | TBC | Not Awarded
ILW EZ | Morgan Sindall | Temporary Site Accommodation | Construction | Framework | NEC-A | B | Complete | 2022-02-10 | 2023-09-30 | TBC | Not Awarded
RAP | Morgan Sindall | Bulk & Bottled Gas Civils (Phase 2 Civils) | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2022-05-06 | 2022-08-04 | 2023-10-31 | TBC | Not Awarded
SCP | Altrad Babcock | Instrument Cabinets | Engineering/Manufacturing | MPP - Fabrication & Manufacture | NEC - SUPPLY | F | Complete | Complete | 2023-10-31 | TBC | Not Awarded
SCP | Altrad Babcock | SIXEP Tie in's (SC) | Engineering/Manufacturing | MPP - Fabrication & Manufacture | NEC - SUPPLY | E | Complete | Complete | 2023-10-31 | 2023-03-15 | Ansaldo Nuclear Limited
RAP | Morgan Sindall | Plant Overview System | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | N/A | 2022-07-12 | 2023-11-30 | TBC | Not Awarded
SRP | Jacobs | Service Supports Design | Design Services / Support | Project - Single Source | NEC PSC | E | N/A | N/A | 2023-11-30 | TBC | Not Awarded
CDE | KBR | Commissioning and Completions (CMS) | IT Hardware and Software | Project - Competitive Tender | Bespoke | E | 2022-10-31 | 2022-11-30 | 2023-11-30 | TBC | Not Awarded
SRP | Morgan Sindall | Glovebox lifting | Mechanical & Pipework | Project - Competitive Tender | NEC | A | Complete | Complete | 2023-11-30 | 2023-04-11 | SCX
RAP | Morgan Sindall | Tower Craneage - ECI / Design | Plant & Equipment and Materials | TBC | NEC | TBC | Complete | 2023-02-28 | 2023-12-31 | TBC | Not Awarded
PPP Services | KBR | Monthly standard option support service order to provide configuration support as instructed by the PPP benefit teams | Consultancy | Project - Sole Source | PS Shortform | A | N/A | N/A | 2023-12-31 | 2023-04-30 | Amplify Now Limited
SRP | Morgan Sindall | Glove Port Covers, Frames & Interlocks | Precision Engineering | Project - Competitive Tender | NEC | E | 2021-06-15 | 2022-02-04 | 2023-12-31 | TBC | Not Awarded
SRP | Morgan Sindall | Monorail main award | Engineering | Project - Single Source | NEC | E | N/A | N/A | 2024-01-31 | TBC | Not Awarded
CDE | KBR | IM Federation & Configuration Hub | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2024-01-31 | TBC | Not Awarded
CDE | KBR | Standard Reference Data | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2024-01-31 | TBC | Not Awarded
CDE | KBR | Specific Tool Interfaces | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2024-01-31 | TBC | Not Awarded
CDE | KBR | General Touch Enabled 3D Interface / data visualisation | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2023-04-14 | TBC | Not Awarded
CDE | KBR | Cats and specs manager | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-04-21 | TBC | Not Awarded
CDE | KBR | Intelligent P&IDs | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2023-04-21 | TBC | Not Awarded
CDE | KBR | Engineered Functional Tag Management | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2024-03-01 | TBC | Not Awarded
CDE | KBR | Intelligent C&I Diagrams & Data | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2024-03-01 | TBC | Not Awarded
CDE | KBR | Intelligent Electrical Diagrams & Data | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2024-03-01 | TBC | Not Awarded
CDE | KBR | Intelligent Multi-Discipline 3D Design | IT Hardware and Software | Project - Sole Source | Bespoke | E | N/A | N/A | 2024-03-21 | TBC | Not Awarded
CDE | KBR | Brownfield 3D Laser Point-Cloud Scanning | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2024-04-01 | TBC | Not Awarded
CDE | KBR | EPMS Tranche B Enterprise Procurement, Materials and Logistics Management System | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2024-04-01 | TBC | Not Awarded
CDE | KBR | Autodesk interface support / clash management / etc | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | N/A | 2023-03-10 | 2024-05-01 | TBC | Not Awarded
CDE | KBR | Laser scans model converter | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | N/A | 2023-03-10 | 2024-05-08 | TBC | Not Awarded
CDE | KBR | Basic CAD Drawing | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | N/A | 2023-03-10 | 2024-07-01 | TBC | Not Awarded
CDE | KBR | Intelligent Building Design | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | N/A | 2023-03-10 | 2024-07-12 | TBC | Not Awarded
CDE | KBR | Intelligent Civils Design with vehicle tracking | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | N/A | 2023-03-10 | 2024-08-02 | TBC | Not Awarded
CDE | KBR | Intelligent Mechanical Design | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | N/A | 2023-03-10 | 2024-08-06 | TBC | Not Awarded
CDE | KBR | Model File & Deliverable Manager | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | N/A | 2023-03-10 | 2024-08-16 | TBC | Not Awarded
CDE | KBR | Multi-Purpose .DWG file Graphic Viewer / Converter | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | N/A | 2023-03-10 | 2024-08-16 | TBC | Not Awarded
CDE | KBR | Consolidated 3D Model Viewer Manager | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | N/A | 2023-03-10 | 2024-08-26 | TBC | Not Awarded
SRP | Jacobs | TW Design Validation Checks | Design Services / Support | Project - Single Source | Bespoke | A | N/A | N/A | 2024-09-01 | 2023-01-11 | Morgan Sindall Engineering Solutions Limited
SCP | Altrad Babcock | Building Lifts | Construction | Project - Single Source | NEC-A | E | Complete | 2022-06-01 | 2024-09-22 | TBC | Not Awarded
SRP | Jacobs | CS&A Support | Design Services / Support | Project - Single Source | NEC PSC | C | N/A | N/A | 2024-10-16 | TBC | Not Awarded
SWMRF | Altrad Babcock | Trial Scoping. Trial 1 - Nuclear Settling Vessel, 2. Deployment trial mast rig and coupling Force Rig, 3. Mobilisation Equip, $. Inclined Plane, 5. Clino Shear, 6. Suspend & Discharge | Design Services / Support | Project - Sole Source | NEC PSC | E | N/A | N/A | 2025-08-04 | TBC | Not Awarded
CDE | KBR | 4D Simulation - Planning & Field Work Apps | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2022-02-28 | TBC | Not Awarded
CDE | KBR | Extract, Load and Transform Platform | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2022-02-28 | TBC | Not Awarded
SRP | Morgan Sindall | Tank Farm | Construction | Project - Competitive Tender | NEC | C | Complete | 2021-12-21 | 2022-03-31 | TBC | Not Awarded
RAP | Morgan Sindall | Glovebox and VXA Fabrication | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC | G | N/A | 2023-02-06 | 2022-06-30 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Asbestos Support (Pre September 2022, Topo etc) | Design Services / Support | Project - Competitive Tender | NEC-E | A | 2023-03-17 | 2023-06-15 | 2022-08-01 | TBC | Not Awarded
SRP | Morgan Sindall | Access Equipment - Crane Hoists | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | 2020-08-05 | 2021-06-29 | 2023-12-31 | TBC | Not Awarded
CDE | KBR | Cost control systems | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-04-30 | 2023-05-31 | 2022-04-01 | TBC | Not Awarded
CDE | KBR | Estimating | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-04-30 | 2023-05-31 | 2022-04-01 | TBC | Not Awarded
CDE | KBR | Decision Empowerment / Process mapping and activity linkage | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-04-30 | 2023-05-31 | 2022-04-01 | TBC | Not Awarded
CDE | KBR | Planning Tool | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2022-04-07 | TBC | Not Awarded
CDE | KBR | Risk identification and Management | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2022-05-25 | TBC | Not Awarded
BEPPS2 | Jacobs | Temporary Works Design ~(MSES) | Design Services / Support | Project - Competitive Tender | Bespoke | D | 2023-04-22 | 2023-07-21 | 2022-06-01 | TBC | Not Awarded
CDE | KBR | Functional Process Plant Design | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2022-06-17 | TBC | Not Awarded
CDE | KBR | Brownfield Photogrammetry Surveying & viewing | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2022-06-17 | TBC | Not Awarded
CDE | KBR | Electrical calculation | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2022-08-30 | TBC | Not Awarded
SRP | Morgan Sindall | Fork Lift Trucks | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | 2024-02-26 | 2024-05-20 | 2022-10-13 | TBC | Not Awarded
SRP | Morgan Sindall | PCM Monitors | Electrical & Instrumentation | Project - Competitive Tender | NEC | A | Complete | 2023-06-05 | 2022-10-14 | TBC | Not Awarded
SRP | Morgan Sindall | Communications -Remote Los | IT Hardware and Software | Project - Competitive Tender | Purchase Order | A | 2023-01-31 | 2023-04-07 | 2022-10-31 | TBC | Not Awarded
CDE | Sellafield | Geospatial Information system (GIS) - pilot | IT Hardware and Software | SL - Term Contract | Bespoke | A | 2023-06-30 | 2023-07-31 | 2023-05-31 | TBC | Not Awarded
CDE | KBR | Construction Management System | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-06-30 | 2023-07-31 | 2023-03-01 | TBC | Not Awarded
CDE | KBR | EPMS Contracts Management solution (EPMS Tranche A) | IT Hardware and Software | Project - Competitive Tender | Bespoke | E | N/A | N/A | 2024-03-31 | TBC | Not Awarded
SRP | Morgan Sindall | Fit Out Process Building- IT equipment | IT Hardware and Software | Project - Competitive Tender | NEC | A | 2023-06-01 | 2023-11-22 | 2023-07-31 | TBC | Not Awarded
CDE | KBR | Benefits Realization / Social Impact Records | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-07-31 | 2023-08-31 | 0 | TBC | Not Awarded
CDE | Sellafield | Stand alone BIM cave for model and other visualisation | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2024-03-01 | TBC | Not Awarded
CDE | KBR | BIM virtual reality and visualisation tool | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-08-01 | TBC | Not Awarded
CDE | KBR | Virtual reality (VR) Immersive / Dynamic Human Interaction | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2024-08-06 | TBC | Not Awarded
SRP | Morgan Sindall | Swab Monitors | Electrical & Instrumentation | Project - Competitive Tender | Purchase Order | B | 2023-07-01 | 2023-10-01 | 2024-12-03 | TBC | Not Awarded
CDE | KBR | Simple organisation chart production from PPP SharePoint lists | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-08-30 | 2023-09-30 | 2025-05-12 | TBC | Not Awarded
CDE | KBR | Learning Management System | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-08-30 | 2023-09-30 | Complete | TBC | Not Awarded
CDE | KBR | Simple video animation tool for preparing training videos | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | Complete | TBC | Not Awarded
Multiple | Jacobs | Design Support | Design Services / Support | Framework | NEC | F | TBC | TBC | TBC | TBC | Not Awarded
SRP | Sellafield | Security Fence (New) | Construction | Project - Competitive Tender | NEC | F | 2022-09-27 | 2022-12-20 | TBC | TBC | Not Awarded
CDE | Sellafield | Geospatial Information system (GIS) - production | IT Hardware and Software | SL - Term Contract | Bespoke | B | 2023-09-30 | 2023-09-30 | TBC | TBC | Not Awarded
CDE | KBR | Permit management | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-09-30 | 2023-09-30 | TBC | TBC | Not Awarded
CDE | KBR | Personnel tracking on site | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-09-30 | 2023-09-30 | TBC | TBC | Not Awarded
CDE | KBR | Lightweight viewer | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | TBC | TBC | Not Awarded
SRP | Morgan Sindall | Statutory Inspections | Support Services | Project - Competitive Tender | NEC-E | B | 2022-11-11 | 2023-02-03 | TBC | TBC | Not Awarded
SRP | Morgan Sindall | Active Commisioning support | Support Services | Project - Competitive Tender | NEC | G | 2023-06-01 | 2023-10-09 | TBC | TBC | Not Awarded
SRP | Morgan Sindall | Training operation and maintenance | Training | Project - Competitive Tender | NEC | A | 2023-06-01 | 2023-10-09 | TBC | TBC | Not Awarded
LSS1 | Morgan Sindall | Main Build Modular Accommodation | Construction | Project - Competitive Tender | NEC | D | 2023-07-01 | 2023-09-01 | TBC | TBC | Not Awarded
LSS1 | Morgan Sindall | CM&I Modules (not standalone package - will be part of the doors/windows packages) | Engineering | Project - Competitive Tender | NEC | B | 2023-09-01 | 2023-11-01 | TBC | TBC | Not Awarded
LSS1 | Morgan Sindall | Modular Accommodation temporary | Construction | MPP - Site Accommodation | NEC | E | 2023-07-01 | 2023-09-01 | TBC | TBC | Not Awarded
SCP | Altrad Babcock | Flask Transfer Bogie | Engineering | MPP - Fabrication & Manufacture | NEC - SUPPLY | B | N/A | 2023-09-18 | TBC | TBC | Not Awarded
LSS1 | Morgan Sindall | Welfare & Maintenance Services | Support Services | Project - Competitive Tender | NEC | D | 2023-01-23 | 2023-09-23 | TBC | TBC | Not Awarded
LSS1 | Morgan Sindall | Architectural Doors | Engineering | Project - Competitive Tender | NEC | D | 2023-08-01 | 2023-10-01 | TBC | TBC | Not Awarded
LSS1 | Morgan Sindall | Radiometrics Equipment | Engineering | Project - Competitive Tender | NEC | B | 2023-10-01 | 2023-12-01 | TBC | TBC | Not Awarded
LSS1 | Morgan Sindall | Universal Shield Blocks | Engineering | Project - Competitive Tender | NEC | G | 2023-09-01 | 2023-11-01 | TBC | TBC | Not Awarded
LSS1 | Morgan Sindall | IT Network BT | IT Hardware and Software | SL - Sole Source | SL Framework | B | 2023-08-17 | 2023-11-15 | TBC | TBC | Not Awarded
SRP | Morgan Sindall | Mech Installation Package Transfer Installation (incl's 000/100/200 IWT & SAT support) | Mechanical & Pipework | Project - Competitive Tender | NEC | G | Complete | 2022-05-06 | TBC | TBC | Not Awarded
SRP | Morgan Sindall | Process Building e.g. Deep Clean, Foreign Material Exclusion | Facilities Management | Project - Competitive Tender | NEC | D | 2023-10-19 | 2024-01-11 | TBC | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Temporary Electric Services | Electrical & Instrumentation | Project - Competitive Tender | NEC-A | C | 2024-01-16 | 2024-04-15 | TBC | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Welfare FM & SHEQ Services (Catering, Fire extinguishers etc) | Facilities Management | Project - Competitive Tender | NEC | G | 2024-01-02 | 2024-03-01 | TBC | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Tower Cranes (Manufacture and Delivery) | Design Services / Support | MPP - Tower Cranes | NEC-E | F | 2023-12-21 | 2024-03-20 | TBC | TBC | Not Awarded
LSS1 | Morgan Sindall | Digital Construction | IT Hardware and Software | Project - Competitive Tender | NEC | A | 2023-07-01 | 2023-09-01 | TBC | TBC | Not Awarded
LSS1 | Morgan Sindall | Site Emergency Phone Line (Copper) | IT Hardware and Software | SL - Sole Source | SL Framework | B | 2023-07-07 | 2023-10-05 | 2022-03-01 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | IT Network (BT Scope) & IT Network (Non BT in SL network / ATOS) | IT Hardware and Software | Project - Sole Source | Bespoke | B | 2023-11-24 | 2024-02-22 | 2022-03-01 | TBC | Not Awarded
SRP | Morgan Sindall | Maintenance Equipment e.g. Pallet Trucks, MEWP's | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | 2023-12-14 | 2024-03-07 | 2022-03-20 | TBC | Not Awarded
LSS1 | Morgan Sindall | Access Controls | Engineering | SL - Sole Source | SL Framework | D | 2023-10-03 | 2024-01-01 | 2022-04-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Chubb Systesms | Engineering | SL - Sole Source | SL Framework | E | 2023-11-05 | 2024-02-03 | 2022-04-01 | TBC | Not Awarded
RAP | Morgan Sindall | HAASC - Mechanical Installation ECI | Mechanical & Pipework | MPP - Fabrication & Manufacture | NEC | A | 2024-09-23 | 2024-01-14 | 2022-04-01 | TBC | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management | Facilities Management | Project - Competitive Tender | NEC | D | 2024-02-09 | 2024-05-03 | 2022-04-01 | TBC | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Security | Facilities Management | Project - Competitive Tender | NEC | A | 2024-02-09 | 2024-05-03 | 2022-04-01 | TBC | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Consumable re-stocking | Facilities Management | Project - Competitive Tender | NEC | A | 2024-02-09 | 2024-05-03 | 2022-04-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Communications/POTS | Engineering | SL - Sole Source | SL Framework | A | 2023-07-07 | 2023-10-05 | 2022-04-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | IT Network Non BT (ATOS) | IT Hardware and Software | SL - Single Source | SL Framework | B | 2023-08-17 | 2023-11-15 | 2022-04-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Commissioning and Testing (provided by the programme) | Engineering | Project - Competitive Tender | NEC | A | 2023-09-29 | 2023-12-28 | 2022-04-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | SHEF Services | Support Services | Project - Competitive Tender | NEC | E | 2022-12-01 | 2023-08-01 | 2022-04-01 | TBC | Not Awarded
SRP | Morgan Sindall | Sheilding Blocks | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | 2022-10-24 | 2024-04-23 | 2022-04-20 | TBC | Not Awarded
LSS1 | Morgan Sindall | IT Infrastructure | Engineering | SL - Sole Source | SL Framework | B | 2023-08-17 | 2023-11-15 | 2022-06-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Crane Rails | Engineering | Project - Sole Source | NEC | C | 2024-01-12 | 2024-04-11 | 2022-08-19 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Shield door inc liners and Out cell shield door recovery system | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | G | 2024-02-20 | 2024-05-20 | 2022-09-26 | TBC | Not Awarded
RAP | Morgan Sindall | PTS System - Pipework/Install | Mechanical & Pipework | MPP - Fabrication & Manufacture | NEC | TBC | N/A | 2024-06-03 | 2023-01-26 | TBC | Not Awarded
SRP | Morgan Sindall | Maintenance Contracts e.g. Preventative Maintenance | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2024-08-07 | 2024-10-30 | 2023-01-23 | TBC | Not Awarded
RAP | Morgan Sindall | HA Secondary Decontamination Cell | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | 2024-10-22 | 2025-01-20 | 2023-04-21 | TBC | Not Awarded
LSS1 | Morgan Sindall | Vault Cranes | Engineering | SL - Sole Source | NEC | G | 2024-10-07 | 2025-01-05 | 2023-03-17 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Control Systems | Electrical & Instrumentation | Project - Competitive Tender | NEC-C | E | 2025-03-18 | 2025-06-16 | 2023-06-30 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Through Wall Lights | Electrical & Instrumentation | MPP - Fabrication & Manufacture | NEC - SUPPLY | E | 2025-03-18 | 2025-06-16 | 2024-03-12 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Large Shielded Plugs | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC - SUPPLY | B | 2025-03-18 | 2025-06-16 | 2022-04-01 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Vault floor plates and support system | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC - SUPPLY | E | 2025-03-18 | 2025-06-16 | 2022-04-08 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Shielded windows inc liners (liners required earlier for construction) | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | E | 2025-03-18 | 2025-06-16 | 2022-04-08 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Mech fabrications | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC - SUPPLY | B | 2025-07-11 | 2025-10-09 | 2022-05-19 | TBC | Not Awarded
SRP | Morgan Sindall | Site Temporary Accommodation - Demoltion | Construction | Project - Competitive Tender | NEC | A | 2025-11-19 | 2026-02-11 | 2022-06-01 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Goods Lift | Plant & Equipment and Materials | Project - Competitive Tender | NEC | D | 2026-02-12 | 2026-05-13 | 2022-06-24 | TBC | Not Awarded
SRP | Morgan Sindall | O&M equipment | Support Services | Project - Competitive Tender | Purchase Order | E | 2026-02-01 | 2026-04-16 | 2022-07-07 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Bogie Rails & end stops (manufacture) | Plant & Equipment and Materials | Project - Sole Source | NEC-A | D | 2026-08-08 | 2026-11-06 | 2022-07-18 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Vent Covers, CMW Sliding platform & Mobile Gamma Gate | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC - SUPPLY | D | 2026-10-28 | 2027-01-26 | 2022-07-21 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Vault Cranes | Plant & Equipment and Materials | Category Management - Sole Source | Bespoke | G | 2026-11-19 | 2027-02-17 | 2022-09-01 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Maintenance cranes | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | E | 2027-01-23 | 2027-04-23 | 2022-12-05 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | PA Doors | Plant & Equipment and Materials | Category Management - Sole Source | Bespoke | D | 2027-08-03 | 2027-11-01 | 2022-12-15 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Test weights and equipment | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | B | 2028-03-08 | 2028-06-06 | 2023-04-28 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | IT Network (Non BT in SL network / ATOS) | IT Hardware and Software | Project - Sole Source | Bespoke | B | 2028-08-29 | 2028-11-27 | 2023-05-30 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | CM&I Plugs | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | A | 2028-12-19 | 2029-03-19 | 2023-05-30 | TBC | Not Awarded
RAP | Morgan Sindall | Stack (Ventilation - HVAC) | HVAC | SL Category Management | NEC | A | N/A | TBC | 2023-07-01 | TBC | Not Awarded
RAP | Morgan Sindall | Vessels and Skids - Place Contract | Plant & Equipment and Materials | SL Category Management | NEC | A | N/A | TBC | 2023-07-24 | TBC | Not Awarded
RAP | Morgan Sindall | Fire Supression - Place Contract | Health & Safety | Project - Competitive Tender | NEC | A | N/A | TBC | 2023-08-28 | TBC | Not Awarded
RAP | Morgan Sindall | Transfer Area Crane - Place Contract - (A1120) | Maintenance | Project - Competitive Tender | NEC | A | TBC | TBC | 2023-10-02 | TBC | Not Awarded
RAP | Morgan Sindall | Radiometrics works | Electrical & Instrumentation | Project - Competitive Tender | NEC | A | TBC | TBC | 2023-10-20 | TBC | Not Awarded
RAP | Morgan Sindall | Analytical Cat D - Place Contract | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | 2023-10-24 | TBC | Not Awarded
RAP | Morgan Sindall | Analytical Cat E - Place Contract | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | 2023-11-21 | TBC | Not Awarded
RAP | Morgan Sindall | Fumecupbards and Open Benches Fabrication | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | 2023-12-01 | TBC | Not Awarded
RAP | Morgan Sindall | HA Commissioning Hall | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | TBC | TBC | 2024-01-08 | TBC | Not Awarded
RAP | Morgan Sindall | HA Transfer Area | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | TBC | TBC | 2024-02-01 | TBC | Not Awarded
RAP | Morgan Sindall | HAASC - Manufacture Design and Fabrication | Mechanical & Pipework | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | 2024-02-28 | TBC | Not Awarded
RAP | Morgan Sindall | Import / Export Bay Crane | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | 2024-06-05 | TBC | Not Awarded
RAP | Morgan Sindall | Internal Transfer Flask - Detail Design | Mechanical & Pipework | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | 2024-06-05 | TBC | Not Awarded
RAP | Morgan Sindall | Internal Transfer Flask - Fabrication | Mechanical & Pipework | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | 2024-07-24 | TBC | Not Awarded
RAP | Morgan Sindall | Internal Transfer System | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | 2024-08-09 | TBC | Not Awarded
RAP | Morgan Sindall | Lifting Equipment | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | 2024-08-09 | TBC | Not Awarded
RAP | Morgan Sindall | MA Cells Fabrication (inc. manufacture design) | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | 2024-08-09 | TBC | Not Awarded
RAP | Morgan Sindall | MA Waste Packages | Mechanical & Pipework | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | 2024-09-01 | TBC | Not Awarded
RAP | Morgan Sindall | Oxygen Depletion System | Electrical & Instrumentation | TBC | NEC | TBC | TBC | TBC | 2025-03-24 | TBC | Not Awarded
RAP | Morgan Sindall | Lifts South Extention - SEB | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | 2026-03-11 | TBC | Not Awarded
RAP | Morgan Sindall | Sample Transfer Cell - Detail Design | Design Services / Support | MPP - Fabrication & Manufacture | NEC PSC | A | TBC | TBC | 2026-09-01 | TBC | Not Awarded
RAP | Morgan Sindall | Sample Transfer Cell - Fabrication | Engineering | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | 2024-02-28 | TBC | Not Awarded
RAP | Morgan Sindall | Shield Doors / Walls | Commodities | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | 2023-06-30 | TBC | Not Awarded
RAP | Morgan Sindall | Transfer Area Crane - Place Contract - (A1120) | Maintenance | Project - Competitive Tender | NEC | TBC | TBC | TBC | 2023-04-30 | TBC | Not Awarded