## Instructions
PPP Procurement Plan
Document Number: PPPG-PR-PLN-00014
Issued for Approval:
Key for the contract value bands:
| A | <£100k
| B | >£100k < £250k
| C | >£250k < £500k
| D | >£500k < £1m
| E | >£1m < £5m
| F | >£5m < £10m
| G | >£10m < £25m
| H | >£25m
Welcome to the latest edition of the PPP Procurement Plan
The purpose of the Procurement Plan is to give you, our current and future supply chain, an insight into what PPP is looking to procure and when, so that you can identify potential opportunities for your organisation.
The Procurement Plan includes: the procuring project; what it is looking to procure; its value; and potential dates for issue of invitation to tender and award.
It also includes a category column, and it is sortable so that you can search and sort by your specific category or categories of interest, or by value, or by date, helping you to quickly identify potential opportunities.
The latest Awarded contracts are also included so that you can track a particular procurement through to award, which further allows you to contact the winning supplier if you feel you may be able to assist them as a sub-supplier.
The Procurement Plan is openly available to all and is equally applicable if you are a large company or an SME. It allows you to see our forward programme of potential work, to use as an opportunities register, and also as a networking tool to build your network of suppliers to the nuclear industry and potential future ventures.
The Procurement Plan does not include details of Key Delivery Partners' individual Call Off Contracts on PPP Major Projects.
If you are interested in any of the packages noted within the Procurement Plan please contact mppsupplychain@sl-ppp.co.uk
As part of its pioneering approach to project delivery and local impact, PPP has engaged with the Swimming with the Big Fish SME Matchmaker Service, which brokers introductions and develops relationships between those bidding to become Key Delivery Partners and high performing SMEs willing to invest in West Cumbria. These SMEs plan to create additional jobs, recruit apprentices and invest to expand/ create new facilities in the West Cumbria as a result of the work they do with their respective Key Delivery Partners.
To find out more about the SME Matchmaker Service, contact hazel.duhy@solomonseurope.co.uk
We are always looking at ways to improve our communications with our supply chain therefore we would welcome any feedback you have to mppsupplychain@sl-ppp.co.uk
Programme and Project Partners (PPP) is a 20-year framework let by Sellafield Ltd in 2019 to improve delivery of its major programmes and projects. PPP is formed by four Lot Partners plus Sellafield Ltd as the fifth Partner. The four Lot Partners are:
KBR – Integration Partner
Jacobs – Design Partner
Morgan Sindall Infrastructure – Construction Partner
Doosan Babcock – Process Construction Partner
The programme of work will be worth approximately £7bn across its 20-year life.
Evolution of the Procurement Plan 2023-2024 and use of CompeteFor
This October 2023 update of the Procurement Plan captues procurements by the PPP Lot Partners only.
As we move in to 2024, PPP will be evolving the approach to procurement planning and advertising and will be:
- Developing the Procurment Plan to include procurements from the Key Delivery Partners (KDPs) so that any KDP requirements are visible to the supply chain. - Partnering with the CompeteFor platform competefor.com so that all opportunities from either the PPP Lot Partners or Key Delivery Partners will be advertised on CompeteFor. PPP and CompeteFor will run sessions to educate the supply chain in how to use CompeteFor, however please feel free to visit the CompeteFor website and register your business.

## Procurement Plan
Project | Procuring Partner | Project Scope / Trade Packs Description | Category 1 | Basis of competition | Contract Type | Value Band | Advert Date | ITT Release Date | Planned Contract Award Date | Actual Contract Award Date | Successful Contractor
RAP | Morgan Sindall | Bundle 4 (WO2) | Engineering | Framework | NEC | E | N/A | N/A | 2022-10-13 | 2022-10-13 | NIS Limited
SRP | Morgan Sindall | ECI interim award for tank farm | Engineering | Project - Competitive Tender | Bespoke | A | Complete | Complete | 2022-12-15 | 2022-12-15 | BOC Limited
RAP | Morgan Sindall | 4D Modelling Resource | Design Services / Support | Project - Competitive Tender | NEC PSC | C | Complete | 2022-10-14 | 2022-12-01 | 2022-12-20 | Oakwood Engineering solutions Limited
SRP | Morgan Sindall | Cranes & Hoists – COTS equipment – Supply & Install | Engineering | Project - Competitive Tender | NEC | D | 2020-08-05 | 2022-03-28 | 2022-12-05 | 2022-12-22 | SCX Special Projects Ltd
SCP | Altrad Babcock | Interconnecting Pipework and pipe bridge sumps (East &West Pipe bridge) | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | G | Complete | 2022-04-01 | 2023-01-23 | 2023-01-23 | Shepley Engineers Limited
RAP | Morgan Sindall | HAASC, MA Cells and SNM Glovebox / VXA ECI | Construction | MPP - Fabrication & Manufacture | NEC | B | Complete | Complete | 2022-10-31 | 2023-02-03 | NIS Limited
SCP | Altrad Babcock | SIXEP Tie in's (SC) | Engineering/Manufacturing | MPP - Fabrication & Manufacture | NEC - SUPPLY | F | Complete | Complete | 2023-03-17 | 2023-03-15 | Ansaldo Nuclear Limited
BEPPS2 | Morgan Sindall | Surveys (Pre September 2022, Topo etc) | Design Services / Support | Project - Competitive Tender | NEC-A | B | 2022-10-22 | 2023-01-20 | 2023-03-31 | 2023-03-30 | CatSurveys Limited
SRP | Morgan Sindall | Glovebox lifting | Mechanical & Pipework | Project - Competitive Tender | NEC | A | Complete | Complete | 2023-04-28 | 2023-04-11 | SCX Special Projects Ltd
SCP | Altrad Babcock | Instrument Cabinets | Engineering/Manufacturing | MPP - Fabrication & Manufacture | NEC - SUPPLY | F | Complete | Complete | 2023-04-24 | 2023-04-24 | Carrs Engineering/Bendalls
ILW EZ | Morgan Sindall | Preparatory Civils Works - accommodation/compound/laydown | Construction | Project - Competitive Tender | NEC-E | B | 2021-12-07 | 2022-03-07 | 2023-04-14 | 2023-04-28 | Stobbarts Ltd
ILW EZ | Morgan Sindall | Temporary Site Accommodation | Construction | MPP - Site Accommodation | Bespoke | B | N/A | 2022-02-10 | 2023-04-21 | 2023-04-30 | Algeco Uk Limited (former Elliotts Group Ltd)
RAP | Morgan Sindall | Bundle 5 (WO2) Prototype and Detailed Design | Engineering | Framework | NEC | E | N/A | 2022-08-23 | 2023-03-13 | 2023-04-30 | Aquila Nuclear Engineering Limited
ILW EZ | Morgan Sindall | Earthworks and Civil Construction Works inc P9 Raw/Potable Water | Construction | Project - Competitive Tender | NEC-C | G | 2022-05-21 | 2022-08-19 | 2023-05-31 | 2023-05-22 | Keltbray Limited
CDE | KBR | PDF viewing, signatures and commenting | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | Complete | Complete | 2023-06-11 | 2023-05-26 | Apex Network Solutions
CDE | KBR | Commissioning and Completions (CMS) | IT Hardware and Software | Project - Competitive Tender | Bespoke | E | 2022-10-31 | 2022-11-30 | 2023-07-31 | 2023-06-14 | Omega Subsea Uk Limited
SCP | Altrad Babcock | Out Cell Crane Assembly | Construction | Project - Competitive Tender | NEC 4 ECC | D | Complete | Complete | 2023-06-23 | 2023-06-23 | SCX Special Projects Ltd
RAP | Morgan Sindall | ITS optioneering contract | Engineering | Project - Competitive Tender | NEC PSC | A | Complete | 2022-11-09 | 2023-06-30 | 2023-08-08 | Bilfinger UK
RAP | Morgan Sindall | Bundle 6 (WO2) Prototyping and Detailed Design | Engineering | Framework | NEC | F | N/A | 2022-10-20 | 2023-08-30 | 2023-08-08 | Orano Limited
SRP | Morgan Sindall | Test Cans | Engineering | Project - Competitive Tender | NEC 3 Supply Contract | D | Complete | Complete | 2023-08-29 | 2023-09-01 | Graham Engineering Limited
SRP | Morgan Sindall | Sealer Coat | Construction | Project - Competitive Tender | NEC 3 ECC | E | Complete | Complete | 2023-09-13 | 2023-09-13 | 3i (Shepley, Jacobs Clean Energy, Altrad Support Services)
RAP | Morgan Sindall | Bulk & Bottled Gas Civils (Phase 2 Civils) | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2022-05-06 | 2022-08-04 | 2023-08-31 | 2023-09-21 | DSD Construction Ltd
CDE | KBR | Autodesk interface support / clash management / etc | IT Hardware and Software | Project - Competitive Tender | Bespoke | E | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Laser scans model converter | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Basic CAD Drawing | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Intelligent Building Design | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Intelligent Civils Design with vehicle tracking | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Intelligent Mechanical Design | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Model File & Deliverable Manager | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Multi-Purpose .DWG file Graphic Viewer / Converter | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
CDE | KBR | Consolidated 3D Model Viewer Manager | IT Hardware and Software | Project - Competitive Tender | Bespoke | H | 2023-03-10 | 2023-03-10 | 2023-10-12 | 2023-10-12 | Symetri Ltd
RAP | Morgan Sindall | SNM Gloveboxes | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC | F | N/A | 2023-02-06 | 2023-11-01 | TBC | Not Awarded | +1
CDE | KBR | EDMS - Comprehensive Document Management system | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | 2021-11-30 | 2022-06-06 | 2023-10-31 | TBC | Not Awarded
SRP | Morgan Sindall | Mech Installation Package Transfer Installation (incl's 000/100/200 IWT & SAT support) | Mechanical & Pipework | Project - Competitive Tender | NEC | G | Complete | 2022-05-06 | 2023-12-01 | TBC | Not Awarded | +1
SRP | Morgan Sindall | Fit Out Process Building- IT equipment | IT Hardware and Software | Project - Competitive Tender | NEC | D | 2023-06-01 | 2023-11-22 | 2023-12-01 | TBC | Not Awarded | +1
SRP | Morgan Sindall | Alimak Hoist Operators | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | Complete | 2023-05-16 | 2023-12-01 | TBC | Not Awarded | +1
SRP | Morgan Sindall | Swob Monitors | Electrical & Instrumentation | Project - Competitive Tender | Purchase Order | B | 2023-07-01 | 2023-10-01 | 2023-12-01 | TBC | Not Awarded
SCP | Jacobs | Fire Stopping Design | Design Services / Support | Project - Competitive Tender | NEC | F | 2023-09-01 | 2023-10-16 | 2023-12-31 | TBC | Not Awarded
SRP | Morgan Sindall | Glove Port Covers, Frames & Interlocks | Precision Engineering | Project - Competitive Tender | NEC | E | 2021-06-15 | 2022-02-04 | 2024-01-31 | TBC | Not Awarded
SCP | Altrad Babcock | interconnecting Pipework and pipe bridge sumps (North services Pipe bridge) | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | D | 2023-11-01 | 2023-12-01 | 2024-02-01 | TBC | Not Awarded
SRP | Morgan Sindall | Statutory Inspections | Support Services | Project - Competitive Tender | NEC-E | B | 2022-11-11 | 2023-02-03 | 2024-02-01 | TBC | Not Awarded
SRP | Morgan Sindall | Active Commissioning support | Support Services | Project - Competitive Tender | NEC | G | 2023-06-01 | 2023-10-09 | 2024-02-28 | TBC | Not Awarded
SRP | Morgan Sindall | Training operation and maintenance | Training | Project - Competitive Tender | NEC | TBC | 2023-06-01 | 2023-10-09 | 2024-02-28 | TBC | Not Awarded
LSS1 | Morgan Sindall | Main Build Modular Accommodation | Construction | Project - Competitive Tender | NEC | D | 2023-07-01 | 2023-09-01 | 2024-03-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | CM&I Modules (not standalone package - will be part of the doors/windows packages) | Engineering | Project - Competitive Tender | NEC | B | 2023-09-01 | 2023-11-01 | 2024-03-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Modular Accommodation temporary | Construction | MPP - Site Accommodation | NEC | E | 2023-07-01 | 2023-09-01 | 2024-03-01 | TBC | Not Awarded
SRP | Morgan Sindall | Masonary / Blockwork | Construction | Project - Competitive Tender | NEC 3 ECC | E | 2022-02-14 | 2022-02-18 | 2024-03-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Welfare & Maintenance Services | Support Services | Project - Competitive Tender | NEC | D | 2023-01-23 | 2023-09-23 | 2024-03-21 | TBC | Not Awarded
CDE | KBR | Cost control systems | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-04-30 | 2023-05-31 | 2024-03-24 | TBC | Not Awarded
CDE | KBR | Decision Empowerment / Process mapping and activity linkage | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-04-30 | 2023-05-31 | 2024-03-24 | TBC | Not Awarded
LSS1 | Morgan Sindall | Architectural Doors | Engineering | Project - Competitive Tender | NEC | D | 2023-08-01 | 2023-10-01 | 2024-04-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Radiometrics Equipment | Engineering | Project - Competitive Tender | NEC | B | 2023-10-01 | 2023-12-01 | 2024-04-01 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building- Alimak Hoist | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | Complete | 2023-11-03 | 2024-04-05 | TBC | Not Awarded
RAP | Morgan Sindall | Process CCTV - Design | Electrical & Instrumentation | Project - Competitive Tender | NEC | A | 2024-12-01 | 2024-01-09 | 2024-04-30 | TBC | Not Awarded
LSS1 | Morgan Sindall | Universal Shield Blocks | Engineering | Project - Competitive Tender | NEC | G | 2023-09-01 | 2023-11-01 | 2024-05-01 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - External Doors | Construction | Project - Competitive Tender | NEC | TBC | 2024-01-02 | 2024-02-29 | 2024-05-09 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - Scaffolding | Access Solutions, Insulation, Painting | Project - Competitive Tender | NEC | TBC | 2024-12-19 | 2024-01-19 | 2024-05-17 | TBC | Not Awarded
PPP Services | KBR | PPE Recycling | Support Services | Project - Competitive Tender | Framework | D | 2024-02-01 | 2024-03-01 | 2024-06-01 | TBC | Not Awarded
PPP Services | KBR | Drug & Alcohol | Support Services | Project - Competitive Tender | Framework | D | 2024-02-01 | 2024-03-01 | 2024-06-01 | TBC | Not Awarded
PPP Services | KBR | PPP Cabins - Cleaning / Catering | Facilities Management | Project - Competitive Tender | Framework | D | 2024-02-01 | 2024-03-01 | 2024-06-01 | TBC | Not Awarded
SCP | Altrad Babcock | Flask Transfer Bogie | Engineering | MPP - Fabrication & Manufacture | NEC - SUPPLY | B | N/A | 2024-01-01 | 2024-06-01 | TBC | Not Awarded
SRP | Morgan Sindall | Process Building e.g. Deep Clean, Foreign Material Exclusion | Facilities Management | Project - Competitive Tender | NEC | D | 2023-10-19 | 2024-01-11 | 2024-06-05 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Temporary Electric Services | Electrical & Instrumentation | Project - Competitive Tender | NEC-A | C | 2024-01-16 | 2024-04-15 | 2024-06-24 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Welfare FM & SHEQ Services (Catering, Fire extinguishers etc) | Facilities Management | Project - Competitive Tender | NEC | G | 2024-01-02 | 2024-03-01 | 2024-06-24 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Tower Cranes (Manufacture and Delivery) | Design Services / Support | MPP - Tower Cranes | NEC-E | F | 2023-12-21 | 2024-03-20 | 2024-06-26 | TBC | Not Awarded
LSS1 | Morgan Sindall | Digital Construction | IT Hardware and Software | Project - Competitive Tender | NEC | A | 2023-07-01 | 2023-09-01 | 2024-07-01 | TBC | Not Awarded
SRP | Morgan Sindall | Maintenance Equipment e.g. Pallet Trucks, MEWP's | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | 2023-12-14 | 2024-03-07 | 2024-07-24 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - Fire Stopping | Construction | Project - Competitive Tender | NEC | TBC | 2024-01-02 | 2024-03-12 | 2024-07-30 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - Fire Encasements | Construction | Project - Competitive Tender | NEC | TBC | 2024-01-02 | 2024-03-12 | 2024-07-30 | TBC | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management | Facilities Management | Project - Competitive Tender | NEC | D | 2024-02-09 | 2024-05-03 | 2024-08-09 | TBC | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Security | Facilities Management | Project - Competitive Tender | NEC | TBC | 2024-02-09 | 2024-05-03 | 2024-08-09 | TBC | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Cleaning | Facilities Management | Project - Competitive Tender | NEC | TBC | 2024-02-09 | 2024-05-03 | 2024-08-09 | TBC | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Consumable re-stocking | Facilities Management | Project - Competitive Tender | NEC | TBC | 2024-02-09 | 2024-05-03 | 2024-08-09 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building Epoxy Floors | Construction | Project - Competitive Tender | NEC | TBC | 2024-01-02 | 2024-05-17 | 2024-08-23 | TBC | Not Awarded
LSS1 | Morgan Sindall | Commissioning and Testing (provided by the programme) | Engineering | Project - Competitive Tender | NEC | A | 2023-09-29 | 2023-12-28 | 2024-08-26 | TBC | Not Awarded
LSS1 | Morgan Sindall | SHEF Services | Support Services | Project - Competitive Tender | NEC | E | 2022-12-01 | 2023-08-01 | 2024-09-01 | TBC | Not Awarded
SRP | Morgan Sindall | Shielding Blocks | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | 2023-10-24 | 2024-04-23 | 2024-09-01 | TBC | Not Awarded
PPP Services | KBR | MP Project Controls | Consultancy | Project - Competitive Tender | Framework | D | 2023-09-07 | 2024-03-01 | 2024-09-01 | TBC | Not Awarded
PPP Services | KBR | MP Commercial | Consultancy | Project - Competitive Tender | Framework | D | 2024-02-01 | 2024-03-01 | 2024-09-01 | TBC | Not Awarded
PPP Services | KBR | MP EHSS&Q | Consultancy | Project - Competitive Tender | Framework | D | 2024-02-01 | 2024-03-01 | 2024-09-01 | TBC | Not Awarded
PPP Services | KBR | MP Project Leadership / Management | Consultancy | Project - Competitive Tender | Framework | D | 2024-02-01 | 2024-03-01 | 2024-09-01 | TBC | Not Awarded
PPP Services | KBR | MP Commissioning & Pre-Ops | Consultancy | Project - Competitive Tender | Framework | D | 2024-02-01 | 2024-03-01 | 2024-09-01 | TBC | Not Awarded
PPP Services | KBR | MP Engineering Design | Consultancy | Project - Competitive Tender | Framework | D | 2024-02-01 | 2024-03-01 | 2024-09-01 | TBC | Not Awarded
PPP Services | KBR | MP Construction | Consultancy | Project - Competitive Tender | Framework | D | 2024-02-01 | 2024-03-01 | 2024-09-01 | TBC | Not Awarded
SRP | Morgan Sindall | Fork Lift Trucks | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | 2024-02-26 | 2024-05-20 | 2024-11-04 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building- Isoclad | Construction | Project - Competitive Tender | NEC | TBC | 2024-03-20 | 2024-06-20 | 2024-11-05 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Shield door inc liners and Out cell shield door recovery system | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | G | 2024-02-20 | 2024-05-20 | 2024-11-11 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - Turnstiles/access | Construction | Project - Competitive Tender | NEC | TBC | 2024-06-01 | 2024-08-01 | 2024-11-21 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - Securiclad Internal Liner | Construction | Project - Competitive Tender | NEC | TBC | 2024-06-01 | 2024-08-01 | 2024-12-19 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - Lifts | Construction | Project - Competitive Tender | NEC | TBC | 2024-04-20 | 2023-07-24 | 2024-12-26 | TBC | Not Awarded
CDE | KBR | Construction Management System | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-06-30 | 2023-07-31 | 2025-01-25 | TBC | Not Awarded
CDE | KBR | Benefits Realization / Social Impact Records | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-07-31 | 2023-08-31 | 2025-01-25 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - Fixtures and Fittings | Construction | Project - Competitive Tender | NEC | TBC | 2024-07-02 | 2024-09-02 | 2025-02-13 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - Washrooms | Construction | Project - Competitive Tender | NEC | TBC | 2024-09-01 | 2024-11-04 | 2025-02-27 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - General Finishes floors and walls | Construction | Project - Competitive Tender | NEC | TBC | 2024-09-05 | 2024-12-02 | 2025-03-23 | TBC | Not Awarded
SRP | Morgan Sindall | Maintenance Contracts e.g. Preventative Maintenance | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2024-08-07 | 2024-10-30 | 2025-03-24 | TBC | Not Awarded
CDE | KBR | Simple organisation chart production from PPP SharePoint lists | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-08-30 | 2023-09-30 | 2025-03-27 | TBC | Not Awarded
CDE | KBR | Learning Management System | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-08-30 | 2023-09-30 | 2025-03-27 | TBC | Not Awarded
CDE | KBR | Permit management | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-09-30 | 2023-09-30 | 2025-03-27 | TBC | Not Awarded
CDE | KBR | Personnel tracking on site | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-09-30 | 2023-09-30 | 2025-03-27 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building- Ceilings | Construction | Project - Competitive Tender | NEC | TBC | 2024-12-09 | 2024-12-02 | 2025-04-24 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - Desks and furniture | Construction | Project - Competitive Tender | NEC | TBC | 2024-11-05 | 2025-02-23 | 2025-06-12 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building - Signage | Construction | Project - Competitive Tender | NEC | TBC | 2025-01-05 | 2025-03-01 | 2025-06-23 | TBC | Not Awarded
SRP | Morgan Sindall | Services Building -Doors | Construction | Project - Competitive Tender | NEC | TBC | 2025-01-05 | 2025-03-01 | 2025-06-23 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Control Systems | Electrical & Instrumentation | Project - Competitive Tender | NEC-C | E | 2025-03-18 | 2025-06-16 | 2025-09-22 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Through Wall Lights | Electrical & Instrumentation | MPP - Fabrication & Manufacture | NEC - SUPPLY | E | 2025-03-18 | 2025-06-16 | 2025-09-22 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Large Shielded Plugs | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC - SUPPLY | B | 2025-03-18 | 2025-06-16 | 2025-09-22 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Vault floor plates and support system | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC - SUPPLY | E | 2025-03-18 | 2025-06-16 | 2025-09-22 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Shielded windows inc liners (liners required earlier for construction) | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | E | 2025-03-18 | 2025-06-16 | 2025-12-08 | TBC | Not Awarded
RAP | Morgan Sindall | Plant Overview System | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | TBC | TBC | 2025-12-17 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Mech fabrications | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC - SUPPLY | B | 2025-07-11 | 2025-10-09 | 2026-01-15 | TBC | Not Awarded
SRP | Morgan Sindall | Site Temporary Accommodation - Demolition | Construction | Project - Competitive Tender | NEC | TBC | 2025-11-19 | 2026-02-11 | 2026-03-11 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Goods Lift | Plant & Equipment and Materials | Project - Competitive Tender | NEC | D | 2026-02-12 | 2026-05-13 | 2026-08-19 | TBC | Not Awarded
SRP | Morgan Sindall | O&M equipment | Support Services | Project - Competitive Tender | Purchase Order | E | 2026-02-01 | 2026-04-16 | 2026-09-01 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Vent Covers, CMW Sliding platform & Mobile Gamma Gate | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC - SUPPLY | D | 2026-10-28 | 2027-01-26 | 2027-05-04 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Vault Cranes | Plant & Equipment and Materials | Category Management - Sole Source | Bespoke | G | 2026-11-19 | 2027-02-17 | 2027-05-26 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Maintenance cranes | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | E | 2027-01-23 | 2027-04-23 | 2027-10-15 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | PA Doors | Plant & Equipment and Materials | Category Management - Sole Source | Bespoke | D | 2027-08-03 | 2027-11-01 | 2028-02-07 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Test weights and equipment | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | B | 2028-03-08 | 2028-06-06 | 2028-11-28 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | CM&I Plugs | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | A | 2028-12-19 | 2029-03-19 | 2029-09-10 | TBC | Not Awarded
RAP | Morgan Sindall | HA Secondary Decontamination Cell | Construction | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Stack (Ventilation - HVAC) | HVAC | SL Category Management | NEC | TBC | N/A | N/A | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Vessels and Skids | Plant & Equipment and Materials | SL Category Management | NEC | TBC | N/A | N/A | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Fire Suppression | Health & Safety | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Transfer Area Crane - Place Contract - (A1120) | Maintenance | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Radiometrics works | Electrical & Instrumentation | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Analytical Cat D | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Analytical Cat E | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | HA Transfer Area | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Fumecupbards and Open Benches Fabrication | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Import / Export Bay Crane | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | HAASC - Manufacture Design and Fabrication | Mechanical & Pipework | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Internal Transfer Flask - Fabrication design and fabrication | Mechanical & Pipework | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Internal Transfer System | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | MA Cells Fabrication (inc. manufacture design) | Plant & Equipment and Materials | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Oxygen Depletion System | Electrical & Instrumentation | TBC | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Lifts South Extension - SEB | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Analytical CAT A1, A2, B & C - Bundles 1 & 2 | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | MA Waste Packages | Mechanical & Pipework | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Sample Transfer Cell - Detail Design | Design Services / Support | MPP - Fabrication & Manufacture | NEC PSC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Secondary Decontamination Unit - ECI | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Secondary Decontamination Unit | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Transfer Area Crane - (A1120) | Maintenance | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | HA Commissioning Hall | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | TBC | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | Shield Doors / Walls | Commodities | MPP - Fabrication & Manufacture | NEC | TBC | N/A | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | SNM Shielded stores | Mechanical & Pipework | Framework | NEC 4 ECC | TBC | N/A | TBC | TBC | TBC | Not Awarded
RAP | Morgan Sindall | In cell process instrumentation/manufacture/supply | Mechanical & Pipework | Framework | NEC 4 ECC | TBC | N/A | TBC | TBC | TBC | Not Awarded