## EXTERNAL INSTRUCTIONS
PPP Procurement Plan
Document Number: PPPG-PR-PLN-00013
Issued for Approval: August 2022
Key for the contract value bands:
| A | <£100k
| B | >£100k < £250k
| C | >£250k < £500k
| D | >£500k < £1m
| E | >£1m < £5m
| F | >£5m < £10m
| G | >£10m < £25m
| H | >£25m
Welcome to the latest quarterly edition of the PPP Procurement Plan.
The purpose of the Procurement Plan is to give you, our current and future supply chain, an insight into what PPP is looking to procure and when, so that you can identify potential opportunities for your organisation.
The Procurement Plan includes: the procuring project; what it is looking to procure; its value band (where available); and potential dates for issue of invitation to tender and award.
It also includes a category column, and it is sortable so that you can search and sort by your specific category or categories of interest, or by value, or by date, helping you to quickly identify potential opportunities.
The latest Awarded contracts are also included so that you can track a particular procurement through to award, which further allows you to contact the winning supplier if you feel you may be able to assist them as a sub-supplier.
The Procurement Plan is openly available to all and is equally applicable if you are a large company or an SME. It allows you to see our forward programme of potential work, to use as an opportunities register, and also as a networking tool to build your network of suppliers to the nuclear industry and potential future ventures.
Please note Key Delivery Partner (KDP) call offs are not included in this plan however the KDPs will release their own procurement plans.
If you are interested in any of the packages noted within the Procurement Plan please contact pppsupplychain@sl-ppp.co.uk
As part of its pioneering approach to project delivery and local impact, PPP has engaged with the Swimming with the Big Fish SME Matchmaker Service, which brokers introductions and develops relationships between those bidding to become Key Delivery Partners and high performing SMEs willing to invest in West Cumbria. These SMEs plan to create additional jobs, recruit apprentices and invest to expand/ create new facilities in the West Cumbria as a result of the work they do with their respective Key Delivery Partners.
To find out more about the SME Matchmaker Service, contact Luke.dicicco@solomonseurope.co.uk
We are always looking at ways to improve our communications with our supply chain therefore we would welcome any feedback you have to clare.wilson@sl-ppp.com
Programme and Project Partners (PPP) is a 20-year framework let by Sellafield Ltd in 2019 to improve delivery of its major programmes and projects. PPP is formed by four Lot Partners plus Sellafield Ltd as the fifth Partner. The four Lot Partners are:
KBR – Integration Partner
Jacobs – Design Partner
Morgan Sindall Infrastructure – Construction Partner
Doosan Babcock – Process Construction Partner
The programme of work will be worth approximately £7bn across its 20-year life.

## EXTERNAL ISSIE
Project | Procuring Partner | Project Scope / Trade Packs Description | Category 1 | Basis of competition | Contract Type | Value Band | EPMS Advert Date | ITT Release Date | Planned Contract Award Date | Actual Contract Award Date | Successful Contractor
BEPPS2 | Morgan Sindall | Surveys (Pre September 2022, Topo etc) | Design Services / Support | Project - Competitive Tender | NEC-A | B | 2022-10-22 | 2023-01-20 | 2023-03-31 | TBC | Not Awarded
ILW EZ | Morgan Sindall | Earthworks and Civil Construction Works inc P9 Raw/Potable Water | Construction | Project - Competitive Tender | NEC-C | G | 2022-05-03 | 2022-08-01 | 2022-12-01 | TBC | Not Awarded
ILW EZ | Jacobs | Preparatory Civils Works - accommodation/compound/laydown | Construction | Project - Competitive Tender | NEC-A | A | 2021-12-07 | 2022-03-07 | 2022-10-30 | TBC | Not Awarded
ILW EZ | Morgan Sindall | Service Connections for accommodation | Utilities | Project - Competitive Tender | NEC-A | A | 2022-01-18 | 2022-04-18 | 2022-10-30 | TBC | Not Awarded
ILW EZ | Morgan Sindall | Raw and Potable Water | Utilities | Project - Competitive Tender | NEC-C | A | 2022-07-21 | 2022-10-19 | 2023-03-02 | TBC | Not Awarded
Multiple | Jacobs | Design Support to Lot 2 | Design Services / Support | Project - Sole Source | NEC PSC | E | 2021-11-03 | 2022-02-01 | 2022-02-28 | 2022-06-22 | 360 Energy
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Sole Source | NEC PSC | E | N/A | 2021-12-13 | 2022-04-01 | 2022-04-01 | Frazer-Nash Consultancy Limited
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Sole Source | NEC PSC | D | N/A | 2021-12-13 | 2022-04-01 | 2022-04-01 | Tenet (Atkins)
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Sole Source | NEC PSC | C | N/A | 2021-12-13 | 2022-04-01 | 2022-04-01 | Wood Group Limited
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Sole Source | NEC PSC | D | N/A | 2021-12-13 | 2022-04-01 | 2022-04-01 | RPS
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Sole Source | NEC PSC | C | N/A | 2021-12-13 | 2022-04-01 | 2022-04-01 | Orano Limited
SRP | Jacobs | Design support for construction | Design Services / Support | Project - Sole Source | Bespoke | A | N/A | 2021-12-01 | 2022-02-01 | 2022-03-29 | IsoClad Limited
Multiple | Jacobs | Design Support to Lot 2 | Design Services / Support | Project - Sole Source | NEC PSC | E | 2021-11-03 | 2022-02-01 | 2022-02-28 | 2022-05-16 | On Line Design & Engineering Limited (OLG)
SRP | Jacobs | Design support for Services supports | Design Services / Support | Project - Sole Source | NEC PSC | C | 2022-05-01 | 2022-08-01 | 2022-09-01 | 2022-09-01 | Hilti GB Limited
Multiple | Jacobs | Contaminated Land Support | Consultancy | Project - Sole Source | Bespoke | C | N/A | Multiple | Multiple | 2022-08-01 | Wood Group Limited
Multiple | Jacobs | Temporary Works Design Validation | Design Services / Support | Project - Sole Source | Bespoke | C | N/A | 2021-11-01 | Multiple | 2022-03-25 | MSES
Multiple | Jacobs | BREXIT and UKCA marking assurance | Consultancy | Project - Sole Source | Bespoke | A | 2021-10-30 | 2022-01-28 | 2022-09-28 | TBC | Not Awarded
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Sole Source | NEC PSC | F | N/A | 2021-12-13 | 2022-04-01 | 2022-04-01 | Assystem Energy & Infrastructure Ltd
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Sole Source | NEC PSC | D | N/A | 2021-12-13 | 2022-04-01 | 2022-04-01 | Morson Projects Ltd
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Sole Source | NEC PSC | F | N/A | 2021-12-13 | 2022-04-01 | 2022-04-01 | Mott Macdonald Limited
SCP | Jacobs | Design support for construction | Design Services / Support | Project - Sole Source | NEC PSC | D | N/A | 2021-12-13 | 2022-04-01 | 2022-04-01 | PWHytek Limited
Multiple | Jacobs | Design Services | Design Services / Support | MPP - Competitive Tender | Framework | H | 2022-03-31 | 2022-06-30 | 2022-11-30 | TBC | Not Awarded
Multiple | KBR | Provision of Bus Services for PPP | Transportation | Project - Sole Source | Framework | E | 2021-11-30 | 2022-02-28 | 2022-03-31 | 2022-05-11 | Stagecoach (North West) Ltd
Multiple | KBR | Provision of PPP PPE and PPE Recycling Framework | Consumables | Project - Sole Source | Framework | E | 2022-01-29 | 2022-04-29 | 2022-06-30 | 2022-06-30 | Bunzl UK Ltd
Multiple | KBR | Provision Integration Servcies for Common Data Environment | IT Hardware and Software | Project - Sole Source | Bespoke | G | N/A | N/A | 2022-09-30 | TBC | Not Awarded
Multiple | KBR | Risk Consultancy | Business Support | Project - Sole Source | NEC | C | Complete | Complete | 2022-01-01 | 2022-01-01 | Optimise Risk Ltd
Multiple | KBR | Risk Consultancy | Business Support | Project - Sole Source | NEC | A | Complete | Complete | 2022-01-17 | 2022-01-17 | The Herne Group (UK) Ltd
PPP Services | KBR | People Management Training | Business Support | Project - Sole Source | NEC | A | Complete | Complete | 2022-01-24 | 2022-01-24 | Wilson & Wilson Learning Ltd
PPP Services | KBR | Consultancy Services - Commercial | Business Support | Project - Sole Source | NEC PSC | A | Complete | Complete | Complete | 2022-02-16 | Walker Sime Limited
PPP Services | KBR | Consultancy Services - Supply Chain Academy | Business Support | Category Management - Competitive Tender | NEC PSC | A | Complete | Complete | Complete | 2022-03-21 | The BidBase
PPP Services | KBR | Software licences | Business Support | Project - Sole Source | Bespoke | B | Complete | Complete | Complete | 2022-04-01 | Tech Data Limited
PPP Services | KBR | IT - hosting service | Business Support | Project - Sole Source | Bespoke | B | Complete | Complete | Complete | 2022-04-01 | Microfocus Limited
PPP Services | KBR | Training - NEC Contracts | Business Support | Project - Sole Source | Bespoke | A | Complete | Complete | Complete | 2022-03-31 | Built Intelligence Ltd
PPP Services | KBR | Consultancy Services - Procurement | Business Support | Project - Sole Source | NEC PSC | D | Complete | Complete | Complete | 2022-04-07 | MACE Limited
PPP Services | KBR | Graphic Design | Business Support | Project - Sole Source | Framework | A | Complete | Complete | Complete | 2022-05-25 | Creative in Cumbria
PPP Services | KBR | WIFI Installation | Business Support | Project - Sole Source | Bespoke | A | Complete | Complete | Complete | 2022-06-01 | Avoria IT Services
Multiple | Morgan Sindall & Doosan Babcock | Groundworks and Concretre Structures | Construction | MPP - Competitive Tender | Framework | H | Complete | 2022-03-31 | 2022-08-31 | TBC | Not Awarded
Multiple | Morgan Sindall & Doosan Babcock | Lot 1 Steel Structures | Construction | MPP - Competitive Tender | Framework | H | Complete | 2022-04-30 | 2022-10-31 | TBC | Not Awarded
Multiple | Morgan Sindall & Doosan Babcock | Lot 2 Cladding & Roofing | Construction | MPP - Competitive Tender | Framework | H | Complete | 2022-04-30 | 2022-10-31 | TBC | Not Awarded
Multiple | Morgan Sindall & Doosan Babcock | Scaffolding Insulation and Painting | Support Services | MPP - Competitive Tender | Framework | H | 2022-03-31 | 2022-06-30 | 2022-12-31 | TBC | Not Awarded
Multiple | Morgan Sindall & Doosan Babcock | Building Fit-Out | Construction | MPP - Competitive Tender | Framework | H | Complete | Complete | 2022-05-10 | 2022-05-10 | Seddons Construction Limited
LSS1 | Morgan Sindall | SHEF Services | Support Services | Project - Competitive Tender | NEC | E | 2022-12-01 | 2023-02-01 | 2024-03-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Welfare & Maintenance Services | Support Services | Project - Competitive Tender | NEC | D | 2023-01-23 | 2023-03-23 | 2023-09-21 | TBC | Not Awarded
LSS1 | Morgan Sindall | Digital Construction | IT Hardware and Software | Project - Competitive Tender | NEC | A | 2023-07-01 | 2023-09-01 | 2024-07-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Main Build Modular Accommodation | Construction | Project - Competitive Tender | NEC | D | 2023-07-01 | 2023-09-01 | 2024-03-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Crane Rails | Engineering | Project - Sole Source | NEC | C | 2024-01-12 | 2024-04-11 | 2024-10-16 | TBC | Not Awarded
LSS1 | Morgan Sindall | Architectural Doors | Engineering | Project - Competitive Tender | NEC | D | 2023-08-01 | 2023-10-01 | 2024-04-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | CM&I Modules (not standalone package - will be part of the doors/windows packages) | Engineering | Project - Competitive Tender | NEC | B | 2023-09-01 | 2023-11-01 | 2024-03-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Universal Shield Blocks | Engineering | Project - Competitive Tender | NEC | G | 2023-09-01 | 2023-11-01 | 2024-05-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Radiometrics Equipment | Engineering | Project - Competitive Tender | NEC | B | 2023-10-01 | 2023-12-01 | 2024-04-01 | TBC | Not Awarded
LSS1 | Morgan Sindall | Vault Cranes | Engineering | Project - Sole Source | NEC | G | 2024-10-07 | 2025-01-05 | 2025-08-04 | TBC | Not Awarded
LSS1 | Morgan Sindall | Access Controls | Engineering | Project - Sole Source | SL Framework | D | 2023-10-03 | 2024-01-01 | 2024-08-02 | TBC | Not Awarded
LSS1 | Morgan Sindall | Chubb Systesms | Engineering | Project - Sole Source | SL Framework | E | 2023-11-05 | 2024-02-03 | 2024-08-06 | TBC | Not Awarded
LSS1 | Morgan Sindall | Commissioning and Testing (provided by the programme) | Engineering | Project - Competitive Tender | NEC | A | 2023-09-29 | 2023-12-28 | 2024-08-26 | TBC | Not Awarded
LSS1 | Morgan Sindall | Communications/POTS | Engineering | Project - Sole Source | SL Framework | A | 2023-07-07 | 2023-10-05 | 2024-08-16 | TBC | Not Awarded
LSS1 | Morgan Sindall | IT Infrastructure | Engineering | Project - Sole Source | SL Framework | B | 2023-08-17 | 2023-11-15 | 2024-09-22 | TBC | Not Awarded
LSS1 | Morgan Sindall | IT Network BT | IT Hardware and Software | Project - Sole Source | SL Framework | B | 2023-08-17 | 2023-11-15 | 2024-05-08 | TBC | Not Awarded
LSS1 | Morgan Sindall | IT Network Non BT (ATOS) | IT Hardware and Software | Project - Sole Source | SL Framework | B | 2023-08-17 | 2023-11-15 | 2024-08-16 | TBC | Not Awarded
LSS1 | Morgan Sindall | Site Emergency Phone Line (Copper) | IT Hardware and Software | Project - Sole Source | SL Framework | B | 2023-07-07 | 2023-10-05 | 2024-07-12 | TBC | Not Awarded
CDE | KBR | PDF viewing, signatures and commenting | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2023-02-28 | TBC | Not Awarded
CDE | KBR | IM Federation & Configuration Hub | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | KBR | Enterprise Integration Hub - Data Integration & transaction tool | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2022-10-31 | 2022-11-30 | 2023-02-28 | TBC | Not Awarded
CDE | KBR | Standard Reference Data | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | KBR | Specific Tool Interfaces | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | KBR | General Touch Enabled 3D Interface / data visualisation | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | Sellafield | Stand alone BIM cave for model and other visualisation | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-11-30 | TBC | Not Awarded
CDE | KBR | EDMS - Comprehensive Document Management system | IT Hardware and Software | Project - Competitive Tender | Bespoke | D | 2021-11-30 | 2022-06-06 | 2022-09-30 | TBC | Not Awarded
CDE | KBR | Cats and specs manager | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | KBR | Autodesk interface support / clash management / etc | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-04-30 | TBC | Not Awarded
CDE | KBR | BIM virtual reality and visualisation tool | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-11-30 | TBC | Not Awarded
CDE | KBR | Laser scans model converter | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-04-30 | TBC | Not Awarded
CDE | KBR | Requirements Management - production | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2023-05-31 | TBC | Not Awarded
CDE | Sellafield | Geospatial Information system (GIS) - pilot | IT Hardware and Software | SL - Term Contract | Bespoke | A | 2023-06-30 | 2023-07-31 | 2023-10-31 | TBC | Not Awarded
CDE | Sellafield | Geospatial Information system (GIS) - production | IT Hardware and Software | SL - Term Contract | Bespoke | B | 2023-09-30 | 2023-09-30 | 2024-01-31 | TBC | Not Awarded
CDE | KBR | Functional Process Plant Design | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2023-09-30 | TBC | Not Awarded
CDE | KBR | Intelligent P&IDs | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | KBR | Engineered Functional Tag Management | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | KBR | Intelligent C&I Diagrams & Data | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | KBR | Intelligent Electrical Diagrams & Data | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | KBR | Intelligent Multi-Discipline 3D Design | IT Hardware and Software | Project - Sole Source | Bespoke | E | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | KBR | Brownfield 3D Laser Point-Cloud Scanning | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | KBR | Brownfield Photogrammetry Surveying & viewing | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-09-30 | TBC | Not Awarded
CDE | KBR | Basic CAD Drawing | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2023-04-30 | TBC | Not Awarded
CDE | KBR | Intelligent Building Design | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2023-04-30 | TBC | Not Awarded
CDE | KBR | Intelligent Civils Design with vehicle tracking | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2023-04-30 | TBC | Not Awarded
CDE | KBR | Intelligent Mechanical Design | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2023-04-30 | TBC | Not Awarded
CDE | KBR | Model File & Deliverable Manager | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-04-30 | TBC | Not Awarded
CDE | KBR | Multi-Purpose .DWG file Graphic Viewer / Converter | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-04-30 | TBC | Not Awarded
CDE | KBR | Consolidated 3D Model Viewer Manager | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-04-30 | TBC | Not Awarded
CDE | KBR | 4D Simulation - Planning & Field Work Apps | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2023-05-31 | TBC | Not Awarded
CDE | KBR | Simple video animation tool for preparing training videos | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-12-31 | TBC | Not Awarded
CDE | KBR | Simple organisation chart production from PPP SharePoint lists | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-08-30 | 2023-09-30 | 2023-12-31 | TBC | Not Awarded
CDE | KBR | Virtual reality (VR) Immersive / Dynamic Human Interaction | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2023-11-30 | TBC | Not Awarded
CDE | KBR | Electrical calculation | IT Hardware and Software | Project - Sole Source | Bespoke | B | N/A | N/A | 2023-09-30 | TBC | Not Awarded
CDE | KBR | Construction Management System | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-06-30 | 2023-07-31 | 2023-10-31 | TBC | Not Awarded
CDE | KBR | Planning Tool | IT Hardware and Software | Project - Sole Source | Bespoke | D | N/A | N/A | 2023-08-31 | TBC | Not Awarded
CDE | KBR | EPMS Tranche B Enterprise Procurement, Materials and Logistics Management System | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-03-31 | TBC | Not Awarded
CDE | KBR | Commissioning and Completions (CMS) | IT Hardware and Software | Project - Competitive Tender | Bespoke | E | 2022-10-31 | 2022-11-30 | 2023-02-28 | TBC | Not Awarded
CDE | KBR | EPMS Contracts Management solution (EPMS Tranche A) | IT Hardware and Software | Project - Sole Source | Bespoke | E | N/A | N/A | 2023-10-31 | TBC | Not Awarded
CDE | KBR | Cost control systems | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-04-30 | 2023-05-31 | 2023-08-31 | TBC | Not Awarded
CDE | KBR | Estimating | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-04-30 | 2023-05-31 | 2023-08-31 | TBC | Not Awarded
CDE | KBR | Benefits Realization / Social Impact Records | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-07-31 | 2023-08-31 | 2023-11-30 | TBC | Not Awarded
CDE | KBR | Learning Management System | IT Hardware and Software | Project - Competitive Tender | Bespoke | C | 2023-08-30 | 2023-09-30 | 2023-12-31 | TBC | Not Awarded
CDE | KBR | Extract, Load and Transform Platform | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-05-31 | TBC | Not Awarded
CDE | Sellafield | Data warehouse for reporting | IT Hardware and Software | SL - Term Contract | Bespoke | A | 2022-10-31 | 2022-11-30 | 2023-02-28 | TBC | Not Awarded
CDE | KBR | Risk identification and Management | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2023-08-31 | TBC | Not Awarded
CDE | KBR | Permit management | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-09-30 | 2023-09-30 | 2024-01-31 | TBC | Not Awarded
CDE | KBR | Personnel tracking on site | IT Hardware and Software | Project - Competitive Tender | Bespoke | B | 2023-09-30 | 2023-09-30 | 2024-01-31 | TBC | Not Awarded
CDE | KBR | Lightweight viewer | IT Hardware and Software | Project - Sole Source | Bespoke | A | N/A | N/A | 2024-01-31 | TBC | Not Awarded
CDE | KBR | Decision Empowerment / Process mapping and activity linkage | IT Hardware and Software | Project - Competitive Tender | Bespoke | A | 2023-04-30 | 2023-05-31 | 2023-08-31 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Temporary Works Design ~(MSES) | Design Services / Support | Project - Sole Source | Bespoke | D | 2023-04-22 | 2023-07-21 | 2023-09-29 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | IT Network (BT Scope) & IT Network (Non BT in SL network / ATOS) | IT Hardware and Software | Project - Sole Source | Bespoke | B | 2023-11-24 | 2024-02-22 | 2024-07-15 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Temporary Electric Services | Electrical & Instrumentation | Project - Competitive Tender | NEC-A | C | 2024-01-16 | 2024-04-15 | 2024-06-24 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Asbestos Support (Pre September 2022, Topo etc) | Design Services / Support | Project - Competitive Tender | NEC-E | A | 2023-03-17 | 2023-06-15 | 2023-08-24 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Minor Civils Care & Maintenance (Gang, Skips, Telehandler etc) | Construction | Project - Sole Source | Bespoke | A | 2023-02-04 | 2023-05-05 | 2023-07-14 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Bogie Rails & end stops (manufacture) | Plant & Equipment and Materials | Project - Sole Source | NEC-A | D | 2026-08-08 | 2026-11-06 | 2027-04-30 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Shielded windows inc liners (liners required earlier for construction) | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | E | 2025-03-18 | 2025-06-16 | 2025-12-08 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Test weights and equipment | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | A | 2028-03-08 | 2028-06-06 | 2028-11-28 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Goods Lift | Plant & Equipment and Materials | MPP | NEC | D | 2026-02-12 | 2026-05-13 | 2026-08-19 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Control Systems | Electrical & Instrumentation | Project - Competitive Tender | NEC-C | E | 2025-03-18 | 2025-06-16 | 2025-09-22 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | IT Network (Non BT in SL network / ATOS) | IT Hardware and Software | Project - Sole Source | Bespoke | B | 2028-08-29 | 2028-11-27 | 2029-05-21 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | CM&I Plugs | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | A | 2028-12-19 | 2029-03-19 | 2029-09-10 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Vault Cranes | Plant & Equipment and Materials | Category Management - Sole Source | Bespoke | G | 2026-11-19 | 2027-02-17 | 2027-05-26 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Maintenance cranes | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | E | 2027-01-23 | 2027-04-23 | 2027-10-15 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | PA Doors | Plant & Equipment and Materials | Category Management - Sole Source | Bespoke | D | 2027-08-03 | 2027-11-01 | 2028-02-07 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Stack Monitoring - NO PROCUREMENT REQUIRED | Plant & Equipment and Materials | Project - Sole Source | NEC | A | 2024-07-11 | 2024-10-09 | 2025-04-02 | 2022-05-30 | 0
BEPPS2 | Morgan Sindall | Shield door inc liners and Out cell shield door recovery system | Plant & Equipment and Materials | Project - Competitive Tender | NEC-A | G | 2024-02-20 | 2024-05-20 | 2024-11-11 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Welfare FM & SHEQ Services (Catering, Fire extinguishers etc) | Facilities Management | Project - Competitive Tender | NEC | G | 0 | 2024-03-01 | 2024-06-24 | TBC | Not Awarded
RAP | Morgan Sindall | Cable Surveys | Construction | Project - Competitive Tender | NEC | C | Complete | Complete | Complete | 2022-02-28 | AVRS Systems Ltd
RAP | Morgan Sindall | Lifting Devices - Place Contract | Plant & Equipment and Materials | SL Category Management | NEC | A | 2023-01-26 | 2023-04-26 | 2023-11-08 | TBC | Mammoet (UK) Limited
RAP | Morgan Sindall | Replace existing BMS | Electrical & Instrumentation | Project - Competitive Tender | NEC | A | Complete | Complete | Complete | 2022-03-03 | Actemium UK Limited
RAP | Morgan Sindall | E01 - Construction Village, Muster Hut & CSCP Mini Civils | Plant & Equipment and Materials | Project - Competitive Tender | NEC | D | N/A | 2022-06-15 | 2022-10-31 | TBC | Not Awarded
RAP | Morgan Sindall | Muster Wireless System | Electrical & Instrumentation | Project - Competitive Tender | NEC | A | 2021-11-26 | 2022-02-24 | 2022-08-11 | TBC | Not Awarded
RAP | Morgan Sindall | Cable Diversions (WP8) | Electrical & Instrumentation | Project - Competitive Tender | NEC | E | N/A | 2022-06-15 | 2022-10-31 | TBC | Not Awarded
RAP | Morgan Sindall | Bulk Gas Breaching Box - (WP9.2) | Construction | SL Category Management | NEC | A | 2022-04-21 | 2022-07-20 | 2023-01-10 | TBC | Not Awarded
RAP | Morgan Sindall | Mox Chillers - (WP10.4) | Plant & Equipment and Materials | Project - Sole Source | NEC | D | 2021-12-22 | 2022-03-22 | 2022-09-07 | TBC | Not Awarded
RAP | Morgan Sindall | New B170.3 Schneider Panel Build - (WP11.1) | Electrical & Instrumentation | Project - Sole Source | NEC | A | N/A | 2022-06-15 | 2022-10-31 | TBC | Not Awarded
RAP | Morgan Sindall | New B170.3 Modular Build- (WP11.2) | Construction | Project - Competitive Tender | NEC | C | N/A | 2022-06-15 | 2022-11-30 | TBC | Not Awarded
RAP | Morgan Sindall | Existing Crane Survey - Place Contract | Consultancy | Project - Sole Source | NEC | C | N/A | 2022-06-01 | 2022-11-11 | TBC | Not Awarded
RAP | Morgan Sindall | Fire Stopping - Place Contract | Health & Safety | MPP - Fire Protection & Detection | NEC | TBC | 2023-03-01 | 2023-05-30 | 2023-12-08 | TBC | Not Awarded
RAP | Morgan Sindall | WP 5.2 Mods to security manufacture | Electrical & Instrumentation | Project - Sole Source | NEC | C | 2023-01-26 | 2023-04-26 | 2023-11-08 | TBC | Not Awarded
RAP | Morgan Sindall | Vessels and Skids - Place Contract | Plant & Equipment and Materials | SL Category Management | NEC | TBC | 2023-01-26 | 2023-04-26 | 2023-11-08 | TBC | Not Awarded
RAP | Morgan Sindall | Doors - Place Contract | Plant & Equipment and Materials | SL Category Management | NEC | TBC | 2023-01-26 | 2023-04-26 | 2023-11-08 | TBC | Not Awarded
RAP | Morgan Sindall | Stack - Place Contract | HVAC | SL Category Management | NEC | TBC | 2023-01-26 | 2023-04-26 | 2023-11-08 | TBC | Not Awarded
RAP | Morgan Sindall | Place contract Fumehoods | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2022-06-16 | 2022-09-14 | 2023-04-04 | TBC | Not Awarded
RAP | Morgan Sindall | Place contract for CAT A, B & C instruments | Plant & Equipment and Materials | Project - Competitive Tender | NEC | C | 2022-02-26 | 2022-05-27 | 2022-10-17 | TBC | Not Awarded
RAP | Morgan Sindall | Transfer Area Crane - Survey | Consultancy | Project - Sole Source | NEC | B | N/A | 2022-10-31 | 2022-12-31 | TBC | Not Awarded
RAP | Morgan Sindall | Transfer Area Crane - Place Contract - (A1120) | Maintenance | Project - Sole Source | NEC | TBC | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | Sample Flask Transfer System - ECI | Mechanical & Pipework | Project - Competitive Tender | NEC | A | 2022-05-13 | 2022-08-11 | 2023-08-11 | TBC | Not Awarded
RAP | Morgan Sindall | Sample Flask Transfer System - Place Contract | Mechanical & Pipework | Project - Sole Source | NEC | TBC | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | HAASC - Specialist Lifting ECI | Mechanical & Pipework | Project - Sole Source | NEC | A | 2022-04-19 | 2022-07-18 | 2023-11-08 | TBC | Not Awarded
RAP | Morgan Sindall | HA Cells 4&5 - Place Contract - Control Valves | Mechanical & Pipework | Project - Competitive Tender | NEC | E | 2022-07-15 | 2022-10-13 | 2023-05-17 | TBC | Not Awarded
RAP | Morgan Sindall | PTS System - Detail Design ECI | Mechanical & Pipework | Project - Competitive Tender | NEC | A | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | Decommissioning Cell - Place Contract | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | Secondary Decontamination - ECI | Mechanical & Pipework | Project - Competitive Tender | NEC | A | 2022-04-15 | 2022-07-14 | 2023-08-11 | TBC | Not Awarded
RAP | Morgan Sindall | Secondary Decontamination - Place Contract | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | Material Control - Place Contract | Mechanical & Pipework | Project - Competitive Tender | NEC | TBC | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | Commissioning Hall - Place Contract | Mechanical & Pipework | Project - Sole Source | NEC | TBC | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | Cameras and Radiometrics - Place Contract - ECI | Electrical & Instrumentation | Project - Sole Source | NEC | TBC | 2023-01-17 | 2023-04-17 | 2023-11-08 | TBC | Not Awarded
RAP | Morgan Sindall | Cameras and Radiometrics - Place Contract | Electrical & Instrumentation | Project - Sole Source | NEC | TBC | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | MSM's - Testing | Plant & Equipment and Materials | Project - Sole Source | NEC | B | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | MSM's - Place Contract | Plant & Equipment and Materials | Project - Sole Source | NEC | TBC | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | Windows - Place Contract - ECI Detail Design | Plant & Equipment and Materials | Project - Sole Source | NEC | TBC | 2022-02-05 | 2022-05-06 | 2023-11-08 | TBC | Not Awarded
RAP | Morgan Sindall | Windows - Place Contract | Plant & Equipment and Materials | Project - Sole Source | NEC | TBC | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | Analytical Cat A1, A2, B & C - Place Contract | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | 2024-01-24 | 2024-04-23 | 2024-11-14 | TBC | Not Awarded
RAP | Morgan Sindall | Strip out works - MPP Civil/Mech/Elect - Place Contract | Decommissioning, Demolition and Deplant | Project - Competitive Tender | NEC | TBC | 2023-05-24 | 2023-08-22 | 2024-03-21 | TBC | Not Awarded
RAP | Morgan Sindall | Security Fortification - Civils Security - Place Contract | Electrical & Instrumentation | Project - Competitive Tender | NEC | B | 2022-07-05 | 2022-10-03 | 2023-05-05 | TBC | Not Awarded
RAP | Morgan Sindall | Security Fortification - Chubb security - Place Contract | Electrical & Instrumentation | Project - Competitive Tender | NEC | B | 2022-07-05 | 2022-10-03 | 2023-05-05 | TBC | Not Awarded
RAP | Morgan Sindall | Plant Overview System | Plant & Equipment and Materials | Project - Competitive Tender | NEC | B | 2022-01-12 | 2022-04-12 | 2023-04-14 | TBC | Not Awarded
RAP | Morgan Sindall | Transfer Systems - ECI | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | 2022-01-12 | 2022-04-12 | 2023-04-14 | TBC | Not Awarded
RAP | Morgan Sindall | Transfer Systems - Place Contract | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | 2023-09-08 | 2023-12-07 | 2024-07-11 | TBC | Not Awarded
RAP | Morgan Sindall | Prefabricated Fumehoods - Place Contract | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | 2023-09-08 | 2023-12-07 | 2024-07-11 | TBC | Not Awarded
RAP | Morgan Sindall | MSM's - Place Contract | Plant & Equipment and Materials | Project - Sole Source | NEC | TBC | 2023-09-08 | 2023-12-07 | 2024-07-11 | TBC | Not Awarded
RAP | Morgan Sindall | Fire Supression - Place Contract | Health & Safety | Project - Competitive Tender | NEC | TBC | 2023-09-08 | 2023-12-07 | 2024-07-11 | TBC | Not Awarded
RAP | Morgan Sindall | MA Cells - Place Contract | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | 2023-09-08 | 2023-12-07 | 2024-07-11 | TBC | Not Awarded
RAP | Morgan Sindall | Misc Tanks - Place Contract | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | 2023-09-08 | 2023-12-07 | 2024-07-11 | TBC | Not Awarded
RAP | Morgan Sindall | Analytical Cat A1, A2, B & C - Place Contract | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | 2023-09-08 | 2023-12-07 | 2024-07-11 | TBC | Not Awarded
RAP | Morgan Sindall | Analytical Cat D - Place Contract | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | 2023-09-08 | 2023-12-07 | 2024-07-11 | TBC | Not Awarded
RAP | Morgan Sindall | Analytical Cat E - Place Contract | Plant & Equipment and Materials | Project - Competitive Tender | NEC | TBC | 2023-09-08 | 2023-12-07 | 2024-07-11 | TBC | Not Awarded
RAP | Morgan Sindall | Windows - Place Contract | Plant & Equipment and Materials | Project - Sole Source | NEC | TBC | 2023-09-08 | 2023-12-07 | 2024-07-11 | TBC | Not Awarded
RAP | Morgan Sindall | Place Level 1A Strip Out Contract - Package 3 MECHANICAL Stripout | Electrical & Instrumentation | Project - Competitive Tender | NEC | E | 2021-10-22 | 2022-01-20 | 2022-10-31 | TBC | Not Awarded
SCP | Doosan Babcock | Building Lifts | Construction | Project - Sole Source | NEC-A | E | Complete | 2022-06-01 | 2022-11-18 | TBC | Otis
SCP | Doosan Babcock | Civils Finishing | Construction | Project - Competitive Tender | NEC-C | G | Complete | Complete | 2022-03-01 | 2022-05-10 | Altrad Support Services Ltd
SCP | Doosan Babcock | Alimaks x2 | Construction | Project - Competitive Tender | Bespoke | E | Complete | Complete | 2022-04-01 | 2022-06-01 | Pegahoist
SCP | Doosan Babcock | Material Handling Equipment (PSC) | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | E | Complete | 2022-02-08 | 2022-06-01 | 2022-06-08 | Hosakowa Micron
SCP | Doosan Babcock | Material Handling Equipment (SC) | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | H | Complete | 2022-02-15 | 2022-10-15 | TBC | Hosakowa Micron
SCP | Doosan Babcock | Control Systems (inc SIXEP Control System) | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | F | Complete | Complete | 2022-08-26 | TBC | Not Awarded
SCP | Doosan Babcock | Interconnecting Pipework and pipe bridge sumps (East &West Pipe bridge) | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | F | Complete | 2022-04-01 | 2022-11-01 | TBC | Not Awarded
SCP | Doosan Babcock | Steam & Air Ejectors | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | E | Complete | Complete | 2022-03-20 | 2022-05-11 | Edwards Ltd
SCP | Doosan Babcock | Pump & Valve Modules | Engineering/Manufacturing | Project - Competitive Tender | NEC - SUPPLY | F | Complete | Complete | 2022-03-01 | 2022-03-09 | West Cumberland Engineering Ltd
SCP | Doosan Babcock | Tanks & Vessels - Free issue Primary Steelwork and Charge Vessels x4 (CAT MAN - Langfields & Bendalls) see T&V scope tab | Engineering/Manufacturing | Category Management - Competitive Tender | Bespoke | D | Complete | 2020-04-28 | 2021-03-31 | TBC | Langfields & Bendalls
SRP | Morgan Sindall | Access Platforms | Plant & Equipment and Materials | Project - Competitive Tender | NEC | H | 2022-10-01 | 2023-01-05 | 2023-05-01 | TBC | Not Awarded
SRP | Morgan Sindall | Swab Monitors | Electrical & Instrumentation | Project - Competitive Tender | Purchase Order | H | 2023-07-01 | 2023-10-01 | 2023-12-01 | TBC | Not Awarded
SRP | Morgan Sindall | Glovebox Spares | Engineering | Project - Sole Source | Purchase Order | H | 2022-04-07 | 2022-07-07 | 2023-10-28 | TBC | Not Awarded
SRP | Morgan Sindall | Fit Out Process Building- IT equipment | IT Hardware and Software | Project - Competitive Tender | NEC | D | 2023-06-01 | 2023-11-22 | 2024-09-10 | TBC | Not Awarded
SRP | Morgan Sindall | Waste management | Waste Management, Disposal & Storage | Project - Competitive Tender | NEC | D | 2022-02-01 | 2022-05-01 | 2022-07-18 | 2022-07-18 | Lawsons
SRP | Morgan Sindall | Communications -Remote Los | IT Hardware and Software | Project - Competitive Tender | Purchase Order | A | 2023-01-31 | 2023-04-07 | 2023-06-22 | TBC | Not Awarded
SRP | Morgan Sindall | Active Commisioning support | Support Services | Project - Competitive Tender | NEC | G | 2023-06-01 | 2023-10-09 | 2024-02-28 | TBC | Not Awarded
SRP | Morgan Sindall | Training operation and maintenance | Training | Project - Competitive Tender | NEC | H | 2023-06-01 | 2023-10-09 | 2024-02-28 | TBC | Not Awarded
SRP | Morgan Sindall | O&M equipment | Support Services | Project - Competitive Tender | Purchase Order | C | 2026-02-01 | 2026-04-16 | 2026-09-01 | TBC | Not Awarded
SRP | Morgan Sindall | Window Shielding - Premac including machining | Precision Engineering | Project - Competitive Tender | NEC | E | 2021-06-15 | 2022-02-04 | 2022-04-01 | 2022-07-25 | Permali Deho Limited
SRP | Morgan Sindall | Glove Port Covers, Frames & Interlocks | Precision Engineering | Project - Competitive Tender | NEC | E | 2021-06-15 | 2022-02-04 | 2022-10-12 | TBC | Not Awarded
SRP | Morgan Sindall | Mech Installation Package Transfer Installation (incl's 000/100/200 IWT & SAT support) | Mechanical & Pipework | Project - Competitive Tender | NEC | H | Complete | 2022-05-06 | 2022-10-28 | TBC | Not Awarded
SRP | Morgan Sindall | Fork Lift Trucks | Plant & Equipment and Materials | Project - Competitive Tender | NEC | A | 2024-02-26 | 2024-05-20 | 2024-10-02 | TBC | Not Awarded
SRP | Sellafield | Security Fence (New) | Construction | Project - Competitive Tender | NEC | F | 2022-09-27 | 2022-12-20 | 2023-04-26 | TBC | Not Awarded
SRP | Morgan Sindall | Discontinued Cans for FAT / IFAT | Precision Engineering | Project - Competitive Tender | NEC | D | 2021-07-19 | 2022-02-10 | 2022-06-01 | 2022-06-08 | Hyde Group Nuclear Ltd
SRP | Morgan Sindall | Access Equipment - Alimak Hoists | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2021-06-11 | 2021-12-17 | 2022-05-19 | 2022-07-26 | Alimak
SRP | Morgan Sindall | Access Equipment - Crane Hoists | Plant & Equipment and Materials | Project - Competitive Tender | NEC | C | 2020-08-05 | 2021-06-29 | 2022-11-28 | TBC | Not Awarded
SRP | Morgan Sindall | Site Temporary Accommodation - Demoltion | Construction | Project - Competitive Tender | NEC | C | 2025-11-19 | 2026-02-11 | 2026-03-11 | TBC | Not Awarded
SRP | Morgan Sindall | 4D Construction Planning | Design Services / Support | Project - Sole Source | NEC | H | N/A | N/A | 2022-08-22 | 2022-08-12 | Prociere
SRP | Morgan Sindall | Service / Welfare Building Facilities Management | Facilities Management | Project - Competitive Tender | NEC | D | 2024-02-09 | 2024-05-03 | 2024-08-09 | TBC | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Security | Facilities Management | Project - Competitive Tender | NEC | H | 2024-02-09 | 2024-05-03 | 2024-08-09 | TBC | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Cleaning | Facilities Management | Project - Competitive Tender | NEC | H | 2024-02-09 | 2024-05-03 | 2024-08-09 | TBC | Not Awarded
SRP | Morgan Sindall | Service / Welfare Building Facilities Management - Consumable re-stocking | Facilities Management | Project - Competitive Tender | NEC | H | 2024-02-09 | 2024-05-03 | 2024-08-09 | TBC | Not Awarded
SRP | Morgan Sindall | Maintenance Equipment e.g. Pallet Trucks, MEWP's | Plant & Equipment and Materials | Project - Competitive Tender | NEC | B | 2023-12-14 | 2024-03-07 | 2024-07-24 | TBC | Not Awarded
SRP | Morgan Sindall | Maintenance Contracts e.g. Preventative Maintenance | Plant & Equipment and Materials | Project - Competitive Tender | NEC | E | 2024-08-07 | 2024-10-30 | 2025-03-24 | TBC | Not Awarded
SRP | Morgan Sindall | Steam Supply – Thorp – on site works Thorp, SPRS, SRP | Mechanical & Pipework | Project - Competitive Tender | NEC | E | 2021-09-29 | 2022-02-11 | 2022-04-08 | 2022-07-05 | Shepley Engineering Limited
SRP | Morgan Sindall | EC&I fire systems | Electrical & Instrumentation | Project - Sole Source | NEC | F | Complete | 2021-11-19 | 2022-04-08 | 2022-04-26 | Protec
SRP | Morgan Sindall | Control Suite Panels | Electrical & Instrumentation | Project - Competitive Tender | NEC | E | Complete | 2021-05-21 | 2022-03-04 | 2022-02-14 | Actemium UK Limited
SRP | Morgan Sindall | Package management - machinery | Plant & Equipment and Materials | Project - Competitive Tender | NEC | G | Complete | 2021-06-22 | 2022-04-01 | 2022-04-01 | Asturfeito SA
SRP | Morgan Sindall | PCM Monitors | IT Hardware and Software | Project Competitive | Purchase Order | H | 2022-10-01 | 2022-12-01 | 2023-04-04 | TBC | Not Awarded
SRP | Morgan Sindall | Cranes & Hoists – COTS equipment – Supply & Install | Engineering | Project - Competitive Tender | NEC | B | 2020-08-05 | 2022-03-28 | 2023-01-27 | TBC | Not Awarded
SRP | Morgan Sindall | Shield Doors | Precision Engineering | Project - Competitive Tender | NEC | E | Complete | 2022-01-31 | 2022-06-24 | 2022-07-15 | Asturfeito SA
SRP | Morgan Sindall | Lifts Process Building – Kone – single source | Construction | Project - Competitive Tender | NEC | D | SSJ | 2022-03-14 | 2023-07-07 | 2022-08-01 | Kone Lifts
SRP | Morgan Sindall | Tank Farm | Construction | Project - Competitive Tender | NEC | B | N/A | 2021-12-21 | 2022-09-30 | TBC | Not Awarded
SRP | Morgan Sindall | Statutory Inspections | Support Services | Project - Competitive Tender | NEC-E | B | 2022-11-11 | 2023-02-03 | 2023-07-28 | TBC | Not Awarded
SRP | Morgan Sindall | Process Building e.g. Deep Clean, Foreign Material Exclusion | Facilities Management | Project - Competitive Tender | NEC | C | 2023-10-19 | 2024-01-11 | 2024-06-05 | TBC | Not Awarded
BEPPS2 | Morgan Sindall | Borehole Sampling and Trailpits - AWARDED | Construction | Project - Competitive Tender | NEC | B | Complete | 2022-03-18 | 2022-05-13 | 2022-05-13 | Socotec
BEPPS2 | Morgan Sindall | DfMA Study - AWARDED | Support Services | MPP - Steelworks & External Envelope | NEC | B | Complete | 2022-01-04 | 2022-03-15 | 2022-03-15 | Balfour Beatty Kilpatrick Limited
UE

## REMOVED SCOPE (hidden)
Project Scope / Trade Packs Description | WBS | WBS No | WBS Category | Trade Pack No | Contract Strategy | Contractual Consideration | Fab /proc Doosan Babcock Package No | Combine with fab / proc pack | Installation Pack No | Package Discipline
Process Condensate Return & CO2 | Internal SIXEP Mod's | 600 | A - Brownfield Mods | 616 | 1 Contract Supply & Install | REMOVED | REMOVED | REMOVED | REMOVED | REMOVED